## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur | SM/07660 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block -Nandigram-I & Nandigram-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000283/2020-2021 | 2974/TD | 25/02/2021 | 06/05/2021 | SANKHA ENTERPRISE | 164.85 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur | SM/07660 | Retrofitting | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000243/2021-2022 | BP-2021-22-66 | 18/08/2021 | 18/08/2021 | SANKHA ENTERPRISE | 70.63 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur | SM/07660 | Retrofitting | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000896/2021-2022 | BP-2021-22-298 | 10/03/2022 | 10/03/2022 | SANKHA ENTERPRISE | 14.19 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur | SM/07660 | Retrofitting | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000895/2021-2022 | BP-2021-22-297 | 10/03/2022 | 10/03/2022 | SANKHA ENTERPRISE | 80 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur | SM/07660 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block -Nandigram-I & Nandigram-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000283/2020-2021 | 2974/TD | 25/02/2021 | 06/05/2021 | SANKHA ENTERPRISE | 164.85 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur | SM/07660 | Retrofitting | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000243/2021-2022 | BP-2021-22-66 | 18/08/2021 | 18/08/2021 | SANKHA ENTERPRISE | 70.63 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur | SM/07660 | Retrofitting | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000896/2021-2022 | BP-2021-22-298 | 10/03/2022 | 10/03/2022 | SANKHA ENTERPRISE | 14.19 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block - Nandigram-I & Nandigram-II in the District of Purba Medinipur | SM/07660 | Retrofitting | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000895/2021-2022 | BP-2021-22-297 | 10/03/2022 | 10/03/2022 | SANKHA ENTERPRISE | 80 | 0 | 0 | 0
Total | [13 empty] | 659.34 | 0 | 0