## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) in the District of Purba Medinipur | SM/07661 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XI (Balance Work) Block ¿ Panskura-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000208/2020-2021 | 2820/TD | 05/02/2021 | 16/04/2021 | TAPAS SANTRA | 196.75 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) in the District of Purba Medinipur | SM/07661 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) under Tamluk Division, PHE Dte. |  |  | VCH/000295/2021-2022 |  | 09/09/2021 | 09/09/2021 | TAPAS SANTRA | 134 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) in the District of Purba Medinipur | SM/07661 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) under Tamluk Division, PHE Dte. |  |  | VCH/000313/2021-2022 | BP-2021-22-78 | 17/09/2021 | 17/09/2021 | TAPAS SANTRA | 134 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) in the District of Purba Medinipur | SM/07661 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Zone ¿ XI (Balance Work) Piped Water Supply Scheme |  |  | VCH/001122/2020-2021 | 1081/W | 30/03/2021 | 30/03/2021 | TAPAS SANTRA | 56.32 | 0 | 0 | 0
Total | [13 empty] | 521.07 | 0 | 0