## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) | SM/07976 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VII(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000195/2020-2021 | 2779/TD | 29/01/2021 | 29/05/2021 | TARUN KOLEY | 253.33 | 506.67 | 200.01 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) | SM/07976 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-I (Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000209/2020-2021 | 2821/TD | 05/02/2021 | 16/05/2021 | M/S A.R. ENTERPRISE | 216.86 | 433.43 | 199.86 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) | SM/07976 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface water Based Water Supply Scheme for Zone-III(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000196/2020-2021 | 2780/TD | 29/01/2021 | 29/05/2021 | JAYANTA KUMAR MONDAL | 259.53 | 512.89 | 197.62 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) | SM/07976 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface water Based Water Supply Scheme for Zone-V(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000198/2020-2021 | 2785/TD | 01/02/2021 | 01/06/2021 | M/S EL-CON | 241.65 | 450.27 | 186.33 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in surface water based water supply scheme under block Panskura-II in the district of Purba Medinipur zone I,III,IV,V,VII,XI (Balance Work) | SM/07976 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface water Based Water Supply Scheme for Zone-IV(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000240/2020-2021 | 2845/TD | 08/02/2021 | 08/06/2021 | CONCORD ENGINEERING | 267.73 | 375.47 | 140.24 | 100
Total | [13 empty] | 1239.1 | 2278.72 | 183.9