## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Amtalia W/S Scheme under Contai-II Deshopran Block(PHASE-II) | SM/08222 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Amtalia PWSS Block- Contai-II in the District of Purba Medinipur.(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000018/2021-2022 | 85/TD | 11/05/2021 | 10/06/2021 | ARABINDA GHOSH | 90.23 | 0 | 0 | 80
Total | [13 empty] | 90.23 | 0 | 0