## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haipur W/S Scheme under Contai-I | SM/08223 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Haipur PWSS Block- Contai-I in the District of Purba Medinipur.(Phase-II) | Assistant Engineer |  | ORD/000279/2020-2021 | 2997/TD | 25/02/2021 | 26/04/2021 | SRIMANTA KUMAR MAITY | 197.96 | 119.39 | 60.31 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haipur W/S Scheme under Contai-I | SM/08223 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Haipur PWSS Block Contai - I in the district of Purba Medinipur under Tamluk Division, PHE Dte. |  |  | VCH/000377/2021-2022 | BP-2021-22-132 | 18/10/2021 | 18/10/2021 | SRIMANTA KUMAR MAITY | 78.57 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haipur W/S Scheme under Contai-I | SM/08223 | Retrofitting | Repair and Renovation of Pump House with Sanitary and water supply arrangement and others allied works for Head works & 2nd Tube well site at Haipur Water Supply Scheme in Contai-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000338/2024-2025 | 3336/TD | 22/10/2024 | 21/11/2024 | SUBHRANGSHU SEKHAR GIRI | 3.06 | 0 | 0 | 0
Total | [13 empty] | 279.59 | 119.39 | 42.7