## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Aladarput W/S Scheme under Contai-II Deshopran Block(PHASE-II) | SM/08227 | Retrofitting | Retrofitting to accomodate FHTC 427 Nos. under JJM Aladarput W/S Scheme within Contai - II Dev. Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000420/2021-2022 | BP-2021-22-93 | 05/10/2021 | 05/10/2021 | BARH CONSTRUCTION | 20.48 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Aladarput W/S Scheme under Contai-II Deshopran Block(PHASE-II) | SM/08227 | Retrofitting | Retrofitting to accomodate FHTC 427 Nos. under JJM Aladarput W/S Scheme within Contai - II Dev. Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000372/2021-2022 |  | 01/10/2021 | 01/10/2021 | BARH CONSTRUCTION | 20.48 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Aladarput W/S Scheme under Contai-II Deshopran Block(PHASE-II) | SM/08227 | Retrofitting | Relaying of 125 mm dia GI Pipe & 150 mm dia GI pipe line for canal crossing with allied works due to damage of pipe line of N.P.-97-99 (part) for construction of culvert of Strengthening & Widening Contai Junput Road of Aladarput Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000264/2021-2022 | 569 / CSD | 08/12/2021 | 29/12/2021 | MRINAL KANTI PRADHAN | 2.24 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Aladarput W/S Scheme under Contai-II Deshopran Block(PHASE-II) | SM/08227 | Retrofitting | Retrofitting to accommodate FHTC [ 427 nos] under JJM in Aladarput PWSS [Sarsa(532, part),Uttar Dauki(549,part),Dakshin Paikbar(574,part),Faridpur(575, part),Biswanathpur(576, part),Aladarput(578, part),Hosenaput(579, part),Kalaminaput(580, part),Dakshin Murabanya(581, part),Bichina(584, part),Purba Chechuraput(585,part )] within Contai-II Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) | Assistant Engineer |  | ORD/000266/2020-2021 | 2919/TD | 22/02/2021 | 14/03/2021 | BARH CONSTRUCTION | 26.62 | 0 | 0 | 100
Total | [13 empty] | 69.83 | 0 | 0