## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dariapur W/S Scheme (PHASE-II) | SM/08230 | Retrofitting | Retrofitting to accomodate FHTC 150 Nos. under Dariapur PWSS within Contai-II Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000422/2021-2022 | BP-2021-22-98 | 05/10/2021 | 05/10/2021 | SK. NUR ISLAM | 10.63 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dariapur W/S Scheme (PHASE-II) | SM/08230 | Retrofitting | Retrofitting to accomodate FHTC 150 Nos. under Dariapur PWSS within Contai-II Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000366/2021-2022 |  | 30/09/2021 | 30/09/2021 | SK. NUR ISLAM | 10.63 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dariapur W/S Scheme (PHASE-II) | SM/08230 | Retrofitting | Retrofitting to accommodate FHTC [ 150 nos] under JJM in Dariapur PWSS [Pratappur(507,part),Haripur(508,part),Ramchak Gopalchak(509,part),Purba Bamunia(511,part), Dariapur(512,part),Daulatpur(513,part),Kazichak(514,part),Chhota Subarnanagar(515,part),Nankar Gopinathpur(516,part),Durgapur Part-IV(608,part)] within Contai-II Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) | Assistant Engineer |  | ORD/000268/2020-2021 | 2921/TD | 22/02/2021 | 14/03/2021 | SK. NUR ISLAM | 10.94 | 0 | 0 | 100
Total | [13 empty] | 32.2 | 0 | 0