## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla W/S Scheme (Phase - II) | SM/08231 | Retrofitting | Laying distribution system of Chirulia-Chatla & its adjoining moujas Water Supply Scheme within Egra-I Dev. Block under Digha sub-division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000261/2021-2022 | 1453/TD | 31/12/2021 | 30/01/2022 | AJIT KUMAR SOM | 29.22 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chirulia-Chatla W/S Scheme (Phase - II) | SM/08231 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chirulia-Chatla PWSS Block- Egra-I in the District of Purba Medinipur.(Phase-II). | Assistant Engineer | Junior Engineer | ORD/000033/2021-2022 | 239/TD | 23/06/2021 | 22/08/2021 | FIROZ KHAN | 172.05 | 67.93 | 39.49 | 100
Total | [13 empty] | 201.26 | 67.93 | 33.75