## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paya(Mahaprabhu) W/S Scheme | SM/08232 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Paya(Mahaprabhu) PWSS Block- Ramnagar-I in the District of Purba Medinipur.(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000280/2020-2021 | 2996/TD | 25/02/2021 | 27/03/2021 | MAITY CONSTRUCTION | 99.11 | 72.39 | 73.04 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paya(Mahaprabhu) W/S Scheme | SM/08232 | Retrofitting | Retrofitting to accomodate FHTC under JJM Paya (Mahaprabhu) W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001108/2020-2021 | 1087/W | 30/03/2021 | 30/03/2021 | MAITY CONSTRUCTION | 24.87 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paya(Mahaprabhu) W/S Scheme | SM/08232 | Retrofitting | valve operator (one no) in head work site at Paya(Mahaprabhu) & its adjoining mouzas water supply scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division PHE Dte. (For 12 months or 365 days) w.e.f from 01.09.2024 |  |  | ORD/000248/2024-2025 | 873/DSD | 27/08/2024 | 27/08/2025 | MAITY CONSTRUCTION | 2.14 | 0 | 0 | 0
Total | [13 empty] | 126.12 | 72.39 | 57.4