## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur W/S Scheme (Phase - II) under Ramnagar-II Block | SM/08233 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kanpur PWSS Block- Ramnagar-II in the District of Purba Medinipur.(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000278/2020-2021 | 2994/TD | 25/02/2021 | 26/04/2021 | BASANTA KUMAR MAITY | 210.56 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur W/S Scheme (Phase - II) under Ramnagar-II Block | SM/08233 | Retrofitting | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Well (Head Work) of Mouza- Barasubarnanagar, JL No.- 502, Plot No.-297 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Ramnagar-II Block of Kanpur Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for 2nd Tube Well of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000108/2022-2023 | 1050/TD | 18/08/2022 | 31/05/2025 | AQUATECH ENGINEERS | 45.52 | 0 | 0 | 98
Total | [13 empty] | 256.08 | 0 | 0