## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Requirement of chemicals, glassware and instrument equipment of Purba Medinipur District Laboratory for NABL Accreditation under Tamluk Division | SM/08683 | Support-WQMSP | Supply, Delivery, Installation & Calibration of Analytical Balance, Distillation Plant required for NABL of Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000198/2021-2022 | 337 / CSD | 21/09/2021 | 01/10/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.62 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Requirement of chemicals, glassware and instrument equipment of Purba Medinipur District Laboratory for NABL Accreditation under Tamluk Division | SM/08683 | Support-WQMSP | Supply of Glassware and Instrument Requirement of Purba Medinipur District Laboratory for NABL Accreditation under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000089/2021-2022 | 571/TD | 25/08/2021 | 09/09/2021 | UTSAV AGENCY | 3.12 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Requirement of chemicals, glassware and instrument equipment of Purba Medinipur District Laboratory for NABL Accreditation under Tamluk Division | SM/08683 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereof for Haldia Sub-District Water Testing Laboratory under Digha Sub-Division, of Tamluk Division, PHE Dte. |  |  | VCH/000230/2022-2023 | BP-2022-23-75 | 10/06/2022 | 10/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Requirement of chemicals, glassware and instrument equipment of Purba Medinipur District Laboratory for NABL Accreditation under Tamluk Division | SM/08683 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereof for Serkhanchak Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000090/2021-2022 | 597/TD | 31/08/2021 | 03/09/2021 | ARUNALOY SCIENTIFIC HOUSE | 4.78 | 0 | 0 | 100
Total | [13 empty] | 14.36 | 0 | 0