## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Jinandapur AWC (19345250319), G.P- Badalpur, (ii) Balarampur AWC (19345250323), G.P- Maitana, (iii) Uttar Kalindi AWC (19345250401), G.P- Kalindi, (iv) Kalindi Basti AWC (19345250405), G.P- Kalindi, (v) Purbabarh Manodamoyee AWC (19345250406), G.P- Kalindi, (vi) Teghari ICDS Centre (19345250409), G.P- Kalindi, (vii) Demuria Paikbar AWC (19345250510), G.P- Maitana, (viii) Mandarpur Pry. School(OWN) (19345250516), G.P- Maitana. | Assistant Engineer |  | ORD/000243/2021-2022 | 1398/TD | 28/12/2021 | 11/02/2022 | MAITY CONSTRUCTION | 23.94 | 22.03 | 92.02 | 100
2 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Patashpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Kaijuddin para-06 (19345220406), G.P- Amarshi 7/1, (ii) Amarshi Kasba-08 (19345220408), G.P- Amarshi 7/1, (iii) Amarshi(e)muslimpara-12 (19345220412), G.P- Amarshi 7/1, (iv) Barsankar-01 (19345220501), (v) Sanamginga-03 (19345220503), G.P- Amarshi 7/2, (vi) Bantitaka-06 (19345220506), (vii) Gumraveri-07 (19345220507), G.P- Amarshi 7/2, (viii) Taladiha-2-08 (19345220508), G.P- Amarshi 7/2. | Assistant Engineer |  | ORD/000247/2021-2022 | 1403/TD | 28/12/2021 | 11/02/2022 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.23 | 21 | 94.48 | 100
3 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakkhin Amtalia Anathbandhu A.W.C. (19345050907), G.P- Amtalia, (ii) Kasafalia A.W.C. (19345050105), G.P- Amtalia, (iii) Aurai Kacharibari A.W.C. (19345050301), G.P- Aurai, (iv) Chhanberya A.W.C. (19345050121), G.P- Aurai, (v) Uttar Basudebberya Bramhanarayan A.W.C. (19345050307), G.P- Aurai, (vi) Namaldiha Mother Teresa A.W.C. (19345050302), G.P- Aurai, (vii) Uttar Karpura Keshabchandra A.W.C. (19345050315), G.P- Aurai, (viii) Sarsa A.W.C. (19345050610), G.P- Bamunia. | Assistant Engineer |  | ORD/000229/2021-2022 | 1360/TD | 24/12/2021 | 07/02/2022 | PARIA ENTERPRISE | 24.53 | 23.27 | 94.88 | 100
4 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 250 mt.) along with stand post at different Sourceless AWC under Contai-III Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Khalsiberia AWC (19345060125), (ii) Marishda AWC (19345060524), G.P- Marishda, (iii) Dakhsin Sukunia (19345060310), (iv) Sukunia Uttar (19345060312), (v) Jagudasbar AWC (19345060413). | Assistant Engineer |  | ORD/000230/2021-2022 | 1361/TD | 24/12/2021 | 28/01/2022 | JASODA ENTERPRISE | 16.04 | 14.11 | 87.93 | 100
5 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Tamluk Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) HOUSE OF SADHAN KUILA,JASADUMBUR (19345281114). G.P- Bishnubarh-I, (ii) MAISALI MAHILA SAMITY HOUSE (19345281118), G.P- Bishnubarh-I, (iii) GHOLECHAK VIJOY PRY. SCH. (19345281119),G.P- Bishnubarh-I, (iv) AMGECHHIA SITALA AWC (19345280915),G.P- Bishnubarh-I, (v) BAHICHARD DAKSHIN PALLI AWC (19345280917),G.P- Bishnubarh-I. | Assistant Engineer |  | ORD/000226/2021-2022 | 1357/TD | 24/12/2021 | 28/01/2022 | BHOLANATH DEY | 14.22 | 14.09 | 99.06 | 100
6 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakshin Veribaranga AWC (19345250122), G.P- Paldhui, (ii) Uttar Kanpur Awc (19345250206), G.P- Depal, (iii) Tajpur AWC (19345250307), G.P- Badalpur, (iv) Badalpur Tarun Sangha Awc (19345250313), G.P- Badalpur. | Assistant Engineer |  | ORD/000271/2021-2022 | 1505/TD | 06/01/2022 | 05/02/2022 | TAPAN BERA | 11.98 | 11.5 | 96 | 100
7 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Block: (i) Sukrasoni (19345240211), G.P- Haldia-I, (ii) Dikshal (19345240216), G.P- Haldia-I, (iii) Khairanda-3 (19345240218), G.P- Haldia-I, (iv) Bandhmuri (19345240219), G.P- Haldia-I, (v) Gangra-1 (19345240312), G.P-Haldia-II, (vi) Gangra-2 (19345240315), G.P- Haldia-II, (vii) Ranisai-2 (19345240322), G.P- Haldia-II, (viii) Koniora-3 (19345240323), G.P- Haldia-II. | Assistant Engineer |  | ORD/000241/2021-2022 | 1396/TD | 28/12/2021 | 11/02/2022 | PALCON | 24.7 | 21.07 | 85.29 | 100
8 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 03 (Three) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Gopalpur (19345240720), G.P- Talgachari-II, (ii) Nariha-2 (19345240802), G.P- Talgachari-I, (iii) Jamra (19345240819), G.P- Talgachari-II. | Assistant Engineer |  | ORD/000242/2021-2022 | 1397/TD | 28/12/2021 | 22/01/2022 | SAYAN MAITY | 9.31 | 8.34 | 89.59 | 100
9 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 39,Rasan Chakbandi FpSchool 23 (19345070323), G.P- Chhatri, (ii) 40,Rasan Own AWC 25 (19345070325), G.P-G.P- Chhatri. | Assistant Engineer |  | ORD/000244/2021-2022 | 1400/TD | 28/12/2021 | 17/01/2022 | GRAND CONSTRUCTION | 5.55 | 5.53 | 99.47 | 100
10 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 28,Baranihari Ramkrishna Seba Sangha 05 (19345070305), G.P- Chhatri, (ii) 30,Ramkrishnapur AWC 03 (19345070303), G.P- Chhatri, (iii) 31, Sannihari Own AWC 14 (19345070314), G.P- Chhatri, (iv) 133, Arjuni ICJCK 21 (19345070821), G.P- Jumki, (v) 134, Hansaria AWC (19345070725), G.P- Jumki, (vi) 136, Chaulda AWC (19345070727), G.P- Jumki,, (vii) 137, Nischinta AWC 27 (19345070827), G.P- Jumki, (viii) 62, Benachakri Mandalpara 24 (19345070424), G.P- Jerthan. | Assistant Engineer |  | ORD/000294/2021-2022 | 1399/TD | 28/12/2021 | 11/02/2022 | AJIT KUMAR SOM | 22.24 | 22.15 | 99.61 | 100
11 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Benagolisa Tapas Mandal House (19345200609), G.P- Gobindanagar, (ii) Ratulia Jr. Basic School (19345200501), G.P- Gobindanagar, (iii) Paschim Arjunda Pry. (19345200502), G.P- Gobindanagar,, (iv) Paschim Nekra Pry. School (19345200505), G.P- Gobindanagar, (v) Joykrishnapur I.C.J.C.K. (19345200507),G.P- Gobindanagar, (vi) Dharmapore Asharam (19345200508), G.P- Gobindanagar, (vii) Manur Pry. School (19345200611), (viii) Golghat Pry. School (19345200613), G.P- Gobindanagar. | Assistant Engineer |  | ORD/000225/2021-2022 | 1356/TD | 24/12/2021 | 07/02/2022 | MADAN MOHAN MAITY | 22.79 | 22.56 | 98.95 | 100
12 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Moyna Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakshin Moyna Badurtala (19345140202), G.P- Moyna-II,(ii) Dakshin Moyna Dangisai (19345140215), G.P- Moyna-II, (iii) P D Moyna (19345140216), G.P- Moyna-II, (iv) Radhaballabh Chak (19345140509), G.P- Gokulnagar. | Assistant Engineer |  | ORD/000227/2021-2022 | 1358/TD | 24/12/2021 | 23/01/2022 | JAGANNATH MAKAR | 12.4 | 12.4 | 99.98 | 100
13 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Mahapur Pry. School G.P. Gobindanagar. (ii) Bijaharpur Nabarun Sangha ( 19345200604), G.P- Gobindanagar, (iii) Rajnagar Pry. School (19345200605), G.P- Gobindanagar, (iv) Anupganj Pry. School (19345200606), G.P- Gobindanagar, (v) Gobindanagar Pry. School(19345200607), G.P- Gobindanagar. | Assistant Engineer |  | ORD/000268/2021-2022 | 1502/TD | 06/01/2022 | 10/02/2022 | BARH CONSTRUCTION | 14.25 | 13.5 | 94.73 | 100
14 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Purba Gurgram-2 No. ICDS (19345010314), G.P- Gurgram, (ii) Amratala AWC (19345010213), G.P- Gurgram. | Assistant Engineer |  | ORD/000252/2021-2022 | 1407/TD | 28/12/2021 | 17/01/2022 | BADAL CHANDRA GOLE | 6.06 | 5.99 | 98.77 | 100
15 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dhelua AWC (19345020309), G.P- Jukhia, (ii) Bani Mandir AWC (19345020312), G.P- Jukhia. | Assistant Engineer |  | ORD/000256/2021-2022 | 1363/TD | 24/12/2021 | 13/01/2022 | DHANANJOY DAS | 6.05 | 5.61 | 92.63 | 100
16 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 64,Kiya Nonformal School 22 (19345070422), G.P- Jerthan, (ii) 66, Ashada 19 (19345070419), G.P- Jerthan, (iii) 59, Satkhanda FP School 02 (19345070402), G.P- Jerthan, (iv) 38,Chhatri Bhatgeria 06 (19345070306), G.P- Chhatri. | Assistant Engineer |  | ORD/000257/2021-2022 | 1365/TD | 24/12/2021 | 23/01/2022 | M/S. S. A. CONSTRUCTION | 11.1 | 11.07 | 99.67 | 100
17 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 240 mt.) along with stand post at different Sourceless AWC under Patashpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Muradpur AWC (19345230101), G.P- Khar, (ii) Manpur AWC (19345230102), G.P- Khar, (iii) Girisha AWC (19345230104), G.P- Khar, (iv) Gangasagar AWC (19345230105), G.P- Khar, (v) Mustafapur Dakshin AWC (19345230107), G.P- Khar, (vi) Bar Mustafapur AWC (19345230108), G.P- Khar, (vii) Panchet Uttar AWC (19345230206), G.P- Panchet-04, (viii) Panchet Daksin AWC (19345230207) | Assistant Engineer |  | ORD/000248/2021-2022 | 1404/TD | 28/12/2021 | 11/02/2022 | GIRI CONSTRUCTION | 25.08 | 24 | 95.69 | 100
18 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Paschimbarh-2 No. ICDS (19345010102), G.P- Mahammadpur-I, (ii) Paschimbarh-3 No. ICDS (19345010103), G.P- Mahammadpur-I, (iii) Uttarbarh-1 No ICDS (19345010104), G.P- Mahammadpur-I, (iv) Sekbarh ICDS (19345010105), G.P- Mahammadpur-I, (v) Mahammadpur-2 No. ICDS (19345010107), G.P- Mahammadpur-I, (vi) Sribachhipur-1 No. ICDS (19345010108), G.P- Mahammadpur-I, (vii) Nimakbarh-2 No. ICDS (19345010113),G.P- Mahammadpur-I, (viii) Uttarbarh-3 No. ICDS (19345010114), G.P- Mahammadpur-I. | Assistant Engineer |  | ORD/000272/2021-2022 | 1506/TD | 06/01/2022 | 20/02/2022 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.25 | 23.52 | 96.99 | 100
19 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 240 mt.) along with stand post at different Sourceless AWC under Patashpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Nimja AWC (19345230213), G.P- Panchet-04, (ii) Bamunda-II AWC (19345230307), G.P- Panchet-04, (iii) Etachana AWC (19345230309), G.P- Panchet-04, (iv) Motirampur AWC (19345230310), G.P- Patashpur-05. | Assistant Engineer |  | ORD/000249/2021-2022 | 1405/TD | 28/12/2021 | 27/01/2022 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12.55 | 11.45 | 91.26 | 100
20 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Rasulpur A.W.C. (19345050911), G.P- Basantia, (ii) Tengorerya Ma Ballavi A.W.C. (19345051007), G.P- Basantia, (iii) Kultalia Paschimpara A.W.C. (19345050915), G.P- Basantia, (iv) Dakkhin Deulpota Subhashchandra A.W.C. (19345051009), G.P- Basantia, (v) Gokulnagar A.W.C. ( 19345050916), G.P- Basantia, (vi) Kalikakumari Vivekananda A.W.C. (19345051010), G.P- Basantia, (vii) Purba Mahammadpur Jana Para A.W.C. (19345051005), G.P- Basantia, (viii) Kultalia Purba Para A.W.C. (19345050914), G.P- Basantia. | Assistant Engineer |  | ORD/000239/2021-2022 | 1394/TD | 28/12/2021 | 11/02/2022 | M/S SREE DURGA ENTERPRISE | 24.51 | 24.23 | 98.87 | 100
21 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakshin Veribaranga AWC (19345250102), G.P- Paldhui, (ii) Kanwa ICDS (19345250105), G.P- Paldhui, (iii) Purba Paldhui AWC (19345250108), G.P- Paldhui, (iv) Uttar Sabitrapur AWC (19345250116), G.P- Paldhui. | Assistant Engineer |  | ORD/000270/2021-2022 | 1504/TD | 06/01/2022 | 05/02/2022 | SUDIP MANNA | 11.98 | 11.05 | 92.2 | 100
22 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Bikra Khan Para (19345200216), G.P- Mysora, (ii) Sahalajpur (Chotto Bhim Para) (19345200218), G.P- Mysora, (iii) Mysora Paschim Muslim Para (19345200124), G.P- Mysora, (iv) Gobindanagar Kali Mandir (19345200603), G.P- Gobindanagar. | Assistant Engineer |  | ORD/000404/2021-2022 | 1896/TD | 23/02/2022 | 25/03/2022 | TARUN KHATUA | 11.39 | 11.29 | 99.08 | 100
23 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Sikarput A.W.C. (19345050705), G.P- Bamunia, (ii) Choudhuribar A.W.C. (19345051011), G.P- Basantia, (iii) Mukundapur Paschim Para A.W.C. (19345051018), G.P- Basantia, (iv) Basantia Mago Mandir A.W.C. (19345051012), G.P- Basantia. | Assistant Engineer |  | ORD/000405/2021-2022 | 1897/TD | 23/02/2022 | 25/03/2022 | FARID UDDIN AHMED | 12.26 | 12.16 | 99.16 | 100
24 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Patashpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Panchuria-2-12 (19345220512), G.P- Amarshi-7/2, (ii) Taladiha-3-13 (19345220513), G.P- Amarshi-7/2. | Assistant Engineer |  | ORD/000388/2021-2022 | 1848/TD | 16/02/2022 | 08/03/2022 | SK. SAHALAM | 5.55 | 5.19 | 93.56 | 100
25 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 240 mt.) along with stand post at different Sourceless AWC under Patashpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Kamalpur AWC (19345230311), G.P- Patashpur-05, (ii) Shikhoda AWC (19345230319), G.P- Patashpur-05, (iii) Morirampur Uttar Awc (19345230322), G.P- Patashpur-05, (iv) Tupchibarh- III AWC (19345230327), G.P- G.P- Patashpur-05. | Assistant Engineer |  | ORD/000389/2021-2022 | 1849/TD | 16/02/2022 | 18/03/2022 | ELECTIVA ENTERPRISE | 12.43 | 11.24 | 90.4 | 100
26 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Porachingra AWC (19345020102), G.P- Garbari-I, (ii) Jhinuk-khali Madhyapally AWC (19345020117), G.P- Garbari-I, (iii) Paschim Garbari AWC (19345020216), G.P- Garbari-II, (iv) Kutubuddinpur AWC (19345020302), G.P- Jukhia, (v) Madhakhali Primary School (19345020303), G.P- Jukhia, (vi) Sitadighi Primary School (19345020305), G.P- Jukhia, (vii) Jukhia AWC (19345020307), G.P- Jukhia, (viii) Jukhia Sitadhighi Primary School (19345020308), G.P- Jukhia. | Assistant Engineer |  | ORD/000456/2021-2022 | 1939/TD | 02/03/2022 | 16/04/2022 | DAS ENTERPRISE | 24.24 | 23.02 | 94.98 | 100
27 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 17,Batashpur FP School 15 (19345070115), G.P- Barida, (ii) 10, Barida Banikishor Sangha 11, (19345070111), G.P- Barida, (iii) 11, Khalina ICJCK 17 (19345070117), G.P- Barida, (iv) 12,Khalina Own Awc 13 (19345070113), G.P- Barida, (v) 13, Madhabpur FP School 16 (19345070116), G.P- Barida, (vi) 194,Sekhpara,Jerthan 08 (19345070408), G.P- Jerthan, (vii) 2, Swarrang Narayan Das'House 06 (19345070106), G.P- Barida, (viii) 190,Sannihari Dhananjoy Patra 15 (19345070315). G.P- Chhatri. | Assistant Engineer |  | ORD/000232/2021-2022 | 1364/TD | 24/12/2021 | 07/02/2022 | S.D. CONSTRUCTION | 22.23 | 22.14 | 99.59 | 100
28 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 270 mt.) along with stand post at different Sourceless AWC under Nandigram-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Amdabad Uttar AWC (19345160504), G.P- Amdabad-I, (ii) Amdabad Purba chara AWC (19345160618), G.P- Amdabad-I, (iii) Amdabad Madhya AWC (19345160502), G.P- Amdabad-I, (iv) Subdi N. State Plan AWC (19345160514), G.P- Amdabad-I, (v) Amdabad 2 N0.AWC (19345160516), G.P- Amdabad-I, (vi) Hanubhuiya Uttar AWC (19345160420),G.P- Birulia, (vii) Sibrampur AWC (19345160422), G.P- Birulia, (viii) Gholpukur Dakshin AWC (19345160409), G.P- Birulia. | Assistant Engineer |  | ORD/000228/2021-2022 | 1359/TD | 24/12/2021 | 07/02/2022 | NARAYAN CHANDRA DAS | 26.82 | 25.2 | 93.96 | 100
29 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Chandanpur-1 (19345240116), G.P- Badhia, (ii) South Badhia-3 (19345240121), G.P- Badhia, (iii) Dangri Patna (19345240125), G.P- Badhia, (iv) Damodarpur Paschim (19345240203), G.P- Badhia, (v) Sadi (19345240207), G.P- Haldia-I, (vi) Kholaberia (19345240208), G.P- Haldia-I, (vii) Nilkanthapur (19345240209), G.P- Haldia-I, (viii) Rania (19345240210), G.P- Haldia-I. | Assistant Engineer |  | ORD/000455/2021-2022 | 1938/TD | 02/03/2022 | 16/04/2022 | AYSAN KHAN | 24.8 | 21.96 | 88.56 | 100
30 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 1.0 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at Sourceless School under Ramnagar-I Dev. Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: Ghersai SSK, G.P- Padima-II, Mouza - Ghersai, J.L. No.- 88 | Assistant Engineer |  | ORD/000131/2022-2023 | 138/RWS/TSD | 14/06/2022 | 21/06/2022 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 2.97 | 2.62 | 88.01 | 100
31 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 1.0 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at Sourceless AWC under Ramnagar-I Dev. Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: Dakshin Badhia AWC, G.P- Badhia, Mouza - Badhia, J.L. No.- 06 | Assistant Engineer |  | ORD/000129/2022-2023 | 135/RWS/TSD | 14/06/2022 | 21/06/2022 | GRAND CONSTRUCTION | 2.98 | 2.59 | 86.89 | 100
32 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 210 mt.) along with stand post at different Sourceless AWC under Egra-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Narubhuiachak ICDS (19345080410), G.P- Bathuary, (ii) Jaganathkarbar Sunrise ICDS ( 193450805414), G.P- Bathuary, (iii) Bhatda Haripur Youth Club (19345080101), G.P- Manjushree, (iv) Bhatda Palli Mongal ICDS (19345080102), G.P- Manjushree. | Assistant Engineer |  | ORD/000246/2021-2022 | 1402/TD | 28/12/2021 | 27/01/2022 | DEBABRATA DAS | 11.69 | 11.63 | 99.48 | 100
33 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 210 mt.) along with stand post at different Sourceless AWC under Egra-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Rukminipur ICDS Centre (19345080302), G.P- Deshbandhu, (ii) Eranda Binapani Club (19345080306), G.P- Deshbandhu, (iii) Kirtipur Bhai Bhai Sangha (19345080307), G.P- Deshbandhu, (iv) Rajendrachak Matsya Jibi Yuva Kalyan Sangha (19345080501), G.P- Deshbandhu, (v) Urijalkar Martri Sakti Sangha (19345080310), G.P- Deshbandhu, (vi) Sarisa Jagrata Yuva Sangha (19345080203), G.P- Deshbandhu, (vii) Hurkuchia Sourav Club (19345080503), G.P- Deshbandhu, (viii) Eranda Haripriya Seba Sangha (19345080309), G.P- Deshbandhu. | Assistant Engineer |  | ORD/000245/2021-2022 | 1401/TD | 28/12/2021 | 11/02/2022 | ABHIJIT BERA | 23.38 | 23.29 | 99.63 | 100
34 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Uttar Tiraipur AWC (19345010201), G.P- Mahammadpur-II, (ii) Benauda 1 No. ICDS (19345010203), G.P- Mahammadpur-II, (iii) Goalapukur AWC (19345010208), G.P- Mahammadpur-II, (iv) Garbhera South ICDS (19345010214), G.P- Gurgram (v) Purba Gurgram-1 No. ICDS (19345010302), G.P- Gurgram, (vi) Dakshin Gurgram ICDS (19345010304), G.P- Gurgram, (vii) Fatepur ICDS (19345010312), G.P- Gurgram, (viii) Buraburi-2 No.ICDS (19345010313), G.P- Gurgram. | Assistant Engineer |  | ORD/000250/2021-2022 | 1406/TD | 28/12/2021 | 11/02/2022 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.23 | 23.51 | 97 | 100
35 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Saiadpur (19345240701), G.P- Talgachari-I, (ii) Uttar Bagpura (19345240712), G.P- Talgachari-I, (iii) Bagpura-2 (19345240714), G.P- Talgachari-I, (iv) Ramnagar (19345240718), G.P- Talgachari-I. | Assistant Engineer |  | ORD/000269/2021-2022 | 1503/TD | 06/01/2022 | 05/02/2022 | SWADHIN KUMAR CHAKRABORTY | 12.43 | 11.57 | 93.09 | 100
36 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 07 (Seven) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Bakshishpur AWC (19345250519), G.P- Maitana, (ii) Dakshin Tentultala AWC (19345250522), G.P- Maitana, (iii) Dakshin Maitana AWC (19345250525), G.P- Maitana, (iv) Satilapur AWC (19345250604), G.P- Sitalapur, (v) Purba Satilapur AWC (19345250605), G.P- Sitalapur, (vi) Purba Ghole AWC (19345250622), G.P- Sitalapur, (vii) Bararankua Harijan AWC (19345250716), G.P- Balisai. | Assistant Engineer |  | ORD/000231/2021-2022 | 1362/TD | 24/12/2021 | 07/02/2022 | MRINAL KANTI PRADHAN | 20.96 | 19.36 | 92.33 | 100
37 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 07 (Seven) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Purba Kusbani A.W.C. (19345050919), G.P- Basantia, (ii) Baghaghole Vivekananda A.W.C. (19345050620), G.P- Chalti, (iii) Dakkhin Kalikapur A.W.C. (19345050619), G.P- Chalti, (iv) Nanker Gopinathpur A.W.C. ( 19345050804) G.P- Dariapur, (v) Chitanyapur A.W.C. (19345050818), G.P- Dariapur, (vi) Haripur A.W.C. (19345050812), G.P- Dariapur, (vii) Uttar Deulpota Padmabati A.W.C. (19345050202), G.P- Dhobaberya. | Assistant Engineer |  | ORD/000240/2021-2022 | 1395/TD | 28/12/2021 | 11/02/2022 | SUBRATA KUMAR BERA | 21.46 | 21.14 | 98.52 | 100
38 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Charaput A.W.C. (19345050612), G.P- Bamunia, (ii) Murabenia Maktab A.W.C. (19345050617), G.P- Bamunia, (iii) Dakshin Kadua A.W.C. (19345050706), G.P- Bamunia (iv) Uttar Kadua Vivekananda A.W.C. (19345050708), G.P- Bamunia. | Assistant Engineer |  | ORD/000406/2021-2022 | 1898/TD | 23/02/2022 | 25/03/2022 | SUBHRANGSHU SEKHAR GIRI | 12.25 | 11.62 | 94.88 | 100
39 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Paschim Bakulda Dashibard AWC (19345200204), G.P- Mysora, (ii) Radhaballavpur P.L.C. (19345200208), G.P- Mysora, (iii) Bikra Pry. School (19345200209), G.P- Mysora, (iv) Rajshar AWC (19345200113), G.P- Mysora, (v) Paschim Shyampur (19345200115), G.P- Mysora, (vi) Purba Mysora Club (19345200117), G.P- Mysora, (vii) Balarampur S.S.K. (19345200211), G.P- Mysora, (viii) Gopal Hazra SSK (19345200213),G.P- Mysora. | Assistant Engineer |  | ORD/000454/2021-2022 | 1937/TD | 02/03/2022 | 16/04/2022 | BIDHAN MONDAL | 22.81 | 21.39 | 93.75 | 100
40 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 210 mt.) along with stand post at different Sourceless AWC under Egra-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Shilampur Swamiji Seba Sangha ( 19345080519), G.P- Vivekananda, (ii) Uttar Eranda Tapsili Sangha (19345080315), G.P- Deshbandhu, (iii) Nijdant Tarun Sangha (19345080316), G.P- Bathuary, (iv) Dakshin Chowmukh ICDS ( 19345080507), G.P- Bathuary, (v) Gangadharbar ICDS Center (19345080508), G.P- Bathuary. | Assistant Engineer |  | ORD/000258/2021-2022 | 1366/TD | 24/12/2021 | 28/01/2022 | ANUPAM CONSTRUCTION | 14.59 | 14.3 | 97.98 | 100
41 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Sinking of 1(One) nos. 100 mm X 50 mm dia. X 220.0 m(av.) depth Indian Mark-II tube well with PVC pipes including cost of all materials and construction of Platform (as per Departtl. approved drawing) at ''Tamralipta Mahavidyalaya'' due to scarcity of drinking water in a newly constructed three- storied building under Tamluk Sub Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer |  | ORD/000328/2023-2024 | 626/TD | 17/05/2023 | 01/06/2023 | GLOBAL TRADE | 2.29 | 2.16 | 94.29 | 100
42 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Diesel Motor Cab/Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage IV) on daily rate basis for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, PHE Dte. from 01.07.2023 to 31.12.2023 (Six) Months. | Assistant Engineer |  | ORD/000529/2023-2024 | 1299/TD | 30/06/2023 | 31/12/2023 | JOY MAA TARA TRAVELS & TRANSPORT | 0.87 | 1.91 | 218.83 | 100
43 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Continuation work order for hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily rate basis (as and when required including Govt. Holiday) for the period from 01.06.2023 to 30.06.2023 i.e. 01 (one) month only, having contract carriage permit from Regional Transport Authority for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. (Ref:- Memo No.- 375/RWS/TSD Dated, 30/11/2022 | Assistant Engineer |  | ORD/000703/2023-2024 | 54/RWS/TSD | 19/05/2023 | 18/06/2023 | SRIMANTA PANJA | 0.14 | 0.38 | 264.19 | 100
44 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | Providing of drinking water supply of different source-less AWCs from different running PWSS under RWS, Tamluk Sub-Division of Tamluk Division. | SM/08698 | New | Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.07.2024 to 31.12.2024 i.e. 06 (Six) Months for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000251/2024-2025 | 104/RWS/TSD | 28/06/2024 | 29/12/2024 | HALADHAR SAMANTA | 0.87 | 2.03 | 232.16 | 50
Total | [13 empty] | 659.44 | 630.13 | 95.56