## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BADHIA PWSS UNDER RAMNAGAR - I BLOCK PHASE II | SM/08745 | Retrofitting | Supply of C.I D.F sluice valve to accommodate FHTC under JJM in BADHYA PWSS Block-Ramnagar-I in the district of Purba Medinipur ( phase -II ) | Assistant Engineer |  | ORD/000349/2021-2022 | 617/DSD | 31/01/2022 | 15/02/2022 | AJIT KUMAR SOM | 1.03 | 1.03 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BADHIA PWSS UNDER RAMNAGAR - I BLOCK PHASE II | SM/08745 | Retrofitting | Rejuvenation to accommodate FHTC (670 nos.) under JJM in BADHIA PWSS Block-Ramnagar-I in the district of Purba Medinipur ( Phase -II ) | Assistant Engineer |  | ORD/000098/2021-2022 | 691/TD | 10/09/2021 | 30/09/2021 | AJIT KUMAR SOM | 94.24 | 89.52 | 94.99 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BADHIA PWSS UNDER RAMNAGAR - I BLOCK PHASE II | SM/08745 | Retrofitting | Laying ( Left Out ) UPVC pipe line to accommodate FHTC under JJM in Badhya PWSS within Ramnagar-I Block ( To support Phase-I FHTC) under Digha Sub-Division of Tamluk Division, PHE Dte. ( Mouza- Kachum, Bakharpur, Khandagram, Badhya) | Assistant Engineer |  | ORD/000543/2021-2022 | 2003/TD | 08/03/2022 | 02/04/2022 | R CONSTRUCTION | 10.79 | 10.79 | 100 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BADHIA PWSS UNDER RAMNAGAR - I BLOCK PHASE II | SM/08745 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 1234/TD | 09/12/2021 | 09/12/2021 | Resource Division | 0.08 | 0 | 0 | 0
Total | [13 empty] | 106.14 | 101.34 | 95.48