## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDHUI PWSS UNDER RAMNAGAR - II BLOCK | SM/08746 | Retrofitting | Retrofitting to accomodate FHTC (1575 nos.) under JJM in Palduhi PWSS Block - RAMNAGAR-II under Digha Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Phase- I) | Assistant Engineer | Junior Engineer | ORD/000007/2021-2022 | 685/TD | 10/09/2021 | 25/10/2021 | BASANTA KUMAR MAITY | 95.95 | 61.88 | 64.49 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDHUI PWSS UNDER RAMNAGAR - II BLOCK | SM/08746 | Retrofitting | Retrofitting to accommodate FHTC 1575 Nos. under JJM in Palduhi PWSS Block Ramnagar - II in the district of Purba Medinipur under Tamluk Division, PHE Dte. |  |  | VCH/000382/2021-2022 | BP-2021-22-135 | 18/10/2021 | 18/10/2021 | BASANTA KUMAR MAITY | 34.05 | 0 | 0 | 0
Total | [13 empty] | 130.01 | 61.88 | 47.6