## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN KANAKPUR PWSS UNDER POTASHPUR - I BLOCK PHASE II | SM/08747 | Retrofitting | Retrofitting to accomodate FHTC (250 nos.) under JJM in Kanakpur PWSS under Potashpur -I Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PHASE-II) | Assistant Engineer |  | ORD/000006/2021-2022 | 684/TD | 10/09/2021 | 30/09/2021 | SRIMANTA KUMAR MAITY | 22.38 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN KANAKPUR PWSS UNDER POTASHPUR - I BLOCK PHASE II | SM/08747 | Retrofitting | Repair and Renovation of Pump House with Sanitary and water supply arrangement and others allied works for Head works & 2nd Tube well site at Kanakpur Water Supply Scheme in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000356/2024-2025 | 3319/TD | 22/10/2024 | 21/11/2024 | THE GODFATHER TRADING COMPANY | 1.45 | 0 | 0 | 0
Total | [13 empty] | 23.83 | 0 | 0