## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN SILAMPUR PWSS UNDER CONTAI - I BLOCK PHASE II | SM/08748 | Retrofitting | Retrofitting to accomodate FHTC (700 nos.) under JJM IN Silampur PWSS under CONTAI-I BLOCK of Contai Sub-Division under Tamluk Division, PHE Dte. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000008/2021-2022 | 686/TD | 10/09/2021 | 10/10/2021 | BASANTA KUMAR MAITY | 58.45 | 0 | 0 | 90
2 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN SILAMPUR PWSS UNDER CONTAI - I BLOCK PHASE II | SM/08748 | Retrofitting | Re-laying of 140 mm dia UPVC pipe line due to Construction of Drain under Dulalpur GP at Silampur Mouza of Silampur W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | Assistant Engineer |  | ORD/000576/2022-2023 | 877 / CSD | 22/11/2022 | 13/12/2022 | JASODA ENTERPRISE | 0.84 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN SILAMPUR PWSS UNDER CONTAI - I BLOCK PHASE II | SM/08748 | Retrofitting | Re-laying of 125 mm dia UPVC & 100 mm dia DI (K-7) pipe line due to Construction of Drain under Dulalpur GP at Silampur Mouza of Silampur W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | Assistant Engineer |  | ORD/000577/2022-2023 | 885 / CSD | 23/11/2022 | 14/12/2022 | PAL ENTERPRISE. | 0.82 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN SILAMPUR PWSS UNDER CONTAI - I BLOCK PHASE II | SM/08748 | Retrofitting | Laying of different dia UPVC pipe line to accommodate 86 nos FHTC to make Betgerya,Eryafetepur, Khalisabhanga,, Betbani, Paryadwip, Silampur, Sitalpur & Sujulpur Mouza as Swajal Gram of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | Assistant Engineer |  | ORD/000522/2022-2023 | 2094 /TD | 13/12/2022 | 02/01/2023 | ROY & ROY CONSTRUCTION. | 5.73 | 0 | 0 | 100
Total | [13 empty] | 65.84 | 0 | 0