## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PASCHIM KAMARDA PWSS UNDER CONTAI - III BLOCK | SM/08750 | Retrofitting | Retrofitting to accomodate FHTC (1487 nos.) under JJM in Paschim Kamarda PWSS Block - Contai-III under Contai Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Phase- I) | Assistant Engineer | Junior Engineer | ORD/000010/2021-2022 | 688/TD | 10/09/2021 | 30/10/2021 | RAJ KUMAR SINGHA | 96.99 | 170.64 | 175.94 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PASCHIM KAMARDA PWSS UNDER CONTAI - III BLOCK | SM/08750 | Retrofitting | Sinking of 2 (two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Tubewell Site (Mouza- Panbhuni, JL No. - 163, Plot No. 551) of Paschim Kamarda Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Replacement of 2nd Tube Tubewell Site (Mouza- Nilpur, JL No. - 160, Plot No. 318) of Paschim Kamarda Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000271/2022-2023 | 1095/TD | 25/08/2022 | 15/09/2022 | M/S SYCHROTECH INDUSTRY | 26.31 | 0 | 0 | 0
Total | [13 empty] | 123.3 | 170.64 | 138.4