## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Central Drilling | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II | SM/08751 | Retrofitting | ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MX200MMX250 MTRS DEPTH) WITH UPVC PIPE BY DIRECT ROTARY RIG MACHINES JOHN-1000 UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000213/2021-2022 | 1402/CDD | 10/02/2022 | 12/03/2022 | ASHUTOSH DAS & CO | 11.32 | 4.77 | 42.14 | 100
2 | PURBA MEDINIPUR |  | Central Drilling | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II | SM/08751 | Retrofitting | additional compressor development of the newly construction tube well at argoal w/s scheme 2nd tw site, block-pataspur -ii under CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000191/2020-2021 | 63/CMSD-I | 18/03/2021 | 21/03/2021 | ASHUTOSH DAS & CO | 0.49 | 0.12 | 24.39 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II | SM/08751 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL ARGOAL W/S SCHEME 2ND TW-II SITE UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000188/2020-2021 | 51 /CMSD-I (D) | 25/02/2021 | 04/03/2021 | ASHUTOSH DAS & CO | 0.95 | 0.95 | 100 | 100
4 | PURBA MEDINIPUR |  | Central Drilling | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II | SM/08751 | Retrofitting | COMPRESSOR DEVELOPMENT OF THE NEWLY CONSTRUCTION TUBE WELL AT ARGOAL W/S SCHEMW 2ND TW SITE, BLOCK-PATASHPUR-II UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000189/2020-2021 | 54/ CMSD-I (D) | 01/03/2021 | 08/03/2021 | WEST BENGAL ENGINEERING CO. | 0.32 | 0.32 | 100 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN ARGOAL PWSS UNDER POTASHPUR - II BLOCK PHASE II | SM/08751 | Retrofitting | Retrofitting to accomodate FHTC (400 nos.) under JJM in Argoal PWSS Block - Potashpur-II under Contai Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Phase - II) | Assistant Engineer | Junior Engineer | ORD/000004/2021-2022 | 682/TD | 10/09/2021 | 30/09/2021 | DAS ENTERPRISE | 44.39 | 35.17 | 79.23 | 100
Total | [13 empty] | 57.48 | 41.34 | 71.92