## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BATHUARI PWSS UNDER EGRA - II BLOCK PHASE II | SM/08752 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bathuary PWSS Block- Egra-II in the District of Purba Medinipur.(Phase-II) |  | Junior Engineer | ORD/000066/2021-2022 | 693/TD | 10/09/2021 | 09/11/2021 | SATYABRATA BHAUMIK | 137.67 | 137.67 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BATHUARI PWSS UNDER EGRA - II BLOCK PHASE II | SM/08752 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 1235/TD | 09/12/2021 | 09/12/2021 | Resource Division | 6.01 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BATHUARI PWSS UNDER EGRA - II BLOCK PHASE II | SM/08752 | Retrofitting | Continuation Work Order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Augmentation Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/001160/2023-2024 | 2566/TD | 06/10/2023 | 05/12/2023 | MISHRA ENTERPRISE | 9.53 | 1.79 | 18.75 | 100
Total | [13 empty] | 153.21 | 139.45 | 91.02