## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR - II BLOCK | SM/08753 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bheribharanga PWSS Block Ramnagar - II in the district of Purba Medinipur under Tamluk Division, PHE Dte. |  |  | VCH/000414/2021-2022 | BP-2021-22-144 | 03/11/2021 | 03/11/2021 | DAS CONSTRUCTION | 37.37 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR - II BLOCK | SM/08753 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bheribaranga PWSS Block- Ramnagar-II in the District of Purba Medinipur.(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000044/2021-2022 | 694/TD | 10/09/2021 | 09/11/2021 | DAS CONSTRUCTION | 97.49 | 60.11 | 61.66 | 80
Total | [13 empty] | 134.86 | 60.11 | 44.57