## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN DAMUDARPUR PWSS UNDER CONTAI - I BLOCK PHASE II | SM/08758 | Retrofitting | Retrofitting to accomodate FHTC (220 nos.) under JJM IN Damudarpur PWSS under Contai-I Block of Contai Sub-Division under Tamluk Division, PHE Dte. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000009/2021-2022 | 687/TD | 10/09/2021 | 30/09/2021 | MAA ANANDAMAYEE | 16.62 | 0 | 0 | 96
Total | [13 empty] | 16.62 | 0 | 0