## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Nandakumar Dev. Block (Av. depth 260 mtr.) = 02 Unit, Mahishadal Dev. Block (Av. depth 260mtr.) = 01 Unit, Sutahata Dev. Block (Av. depth 260 mtr.) = 02 Unit & Kolaghat Dev. Block (Av. depth 205 mtr.) = 01 Unit ] Total 06 Unit. | Assistant Engineer |  | ORD/000280/2021-2022 | 1529/TD | 11/01/2022 | 25/02/2022 | ARABINDA GHOSH | 69.7 | 65.53 | 94.02 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Deshpran Dev. Block (Av. depth 230 mtr.) = 01 Unit ] Total 01 Unit. Name of Site : i) G.P.- Basntia, Mouza- Purba Mukundapur, J.L. No.- 488, Plot No.- 120 under Deshpran Dev. Block | Assistant Engineer |  | ORD/000279/2021-2022 | 1528/TD | 11/01/2022 | 31/01/2022 | SUBRATA KUMAR BERA | 11.09 | 11.03 | 99.46 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Ramnagar-I Dev. Block (Av. depth 230mtr.) = 01 Unit, Ramnagar-II Dev. Block (Av. depth 205mtr.) = 02 Unit & Egra-II Dev. Block (Av. depth 205mtr.) = 02 Unit ] Total 05 Unit. Name of Site : i) G.P.- Talgachari-I, Mouza- Talgachari, J.L. No.-108, Plot No.- 633 under Ramnagar-I Dev. Block, ii) G.P.- Balisai, Mouza- Bararankua, J.L. No.-200, Plot No.-307 under Ramnagar-II Dev. Block, iii) G.P.-Maithana, Mouza - Demuria Paikbar, J.L. No.-142, Plot No.-275 under Ramnagar-II Dev. Block, iv) G.P.- Paniparul, Mouza -Paniparul, J.L. No.-203, Plot No.-3329 under Egra-II Dev. Block & v) G.P.- Dubda, Mouza- Dubda, J.L. No.-191, Plot No.-38 under Egra-II Dev. Block. | Assistant Engineer |  | ORD/000277/2021-2022 | 1526/TD | 11/01/2022 | 25/02/2022 | BASANTA KUMAR MAITY | 53.79 | 53.72 | 99.87 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Contai-I Dev. Block (Av. depth 205 mtr.) = 01 Unit & Contai-III Dev. Block (Av. depth 260 mtr.) = 01 Unit ] Total 02 Unit. Name of Site : i) G.P.- Sabajpur, Mouza- Sabajpur, J.L. No.- 296, Plot No.- 503 under Contai-I Dev. Block, & ii) G.P.- Debendra, Mouza- Balageria, J.L. No.- 79, Plot No.- 250 under Contai-III Dev. Block, | Assistant Engineer, Headquaters |  | ORD/000278/2021-2022 | 1527/TD | 11/01/2022 | 10/02/2022 | SRIMANTA KUMAR MAITY | 22.46 | 10.79 | 48.04 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Bhagwanpur-I Dev. Block (Av. depth 230 mtr.) = 03 Unit & Khejuri-II Dev. Block (Av. depth 260 mtr.) = 02 Unit ] Total 05 Unit. | Assistant Engineer |  | ORD/000283/2021-2022 | 1532/TD | 11/01/2022 | 25/02/2022 | MIDNAPUR PIPE CONCERN | 50.45 | 48.67 | 96.48 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Chandipur Dev. Block (Av. depth 230 mtr.) = 02 Unit, Haldia Dev. Block (Av. depth 260mtr.) = 01 Unit, Panskura-I Dev. Block (Av. depth 205 mtr.) = 01 Unit & Patashpur-II Dev. Block (Av. depth 230 mtr.) = 02 Unit ] Total 06 Unit. | Assistant Engineer |  | ORD/000282/2021-2022 | 1531/TD | 11/01/2022 | 25/02/2022 | EQUIPMENTS AND SPARES AGENCIES | 64.74 | 63.36 | 97.87 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Khejuri-II Dev. Block (Av. depth 260 mtr.) = 01 Unit ] Total 01Unit. Name of Site : i) G.P.- Nijkasba, Mouza- Thanaberia, J.L. No.- 98, Plot No.- 328 under Khejuri-II Dev. Block. | Assistant Engineer |  | ORD/000051/2022-2023 | 296/TD | 06/05/2022 | 31/05/2022 | SK. NUR ISLAM | 11.05 | 10.88 | 98.47 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the New Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Tamluk Dev. Block (Av. depth 205 mtr.) = 03 Unit, Sahid Matangini Dev. Block (Av. depth 205mtr.) = 01 Unit & Egra-II Dev. Block (Av. depth 205mtr.) = 02 Unit ] Total 06 Unit. Name of Site : i) G.P.- Anantapur-I, Mouza- Maisali, J.L. No.-127, Plot No.- 16 under Tamluk Dev. Block, ii) G.P.- Municipality, Mouza- Daharpur, J.L. No.- 276, Plot No.- 442 under Tamluk Dev. Block, iii) G.P.- Pipulberia-I, Mouza - Gaurangapur, J.L. No.-150, Plot No.- 373 under Tamluk Dev. Block, iv) G.P.- Balluk-I, Mouza - Janubasan RH, J.L. No.- 44, Plot No.- 40 under Sahid Matangini Dev. Block, v) G.P.- Sarbodaya, Mouza- Naskarpur, J.L. No.-262, Plot No.- 120 under Egra-II Dev. Block & vi) G.P.- Basudevpur, Mouza- Shyamharibar, J.L. No.- 266, Plot No.- 3611 under Egra-II Dev. Block. | Assistant Engineer |  | ORD/000045/2022-2023 | 175/TD | 25/04/2022 | 09/06/2022 | CHANDA AGENCIES | 62.48 | 59.93 | 95.93 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | SM/08759 | Retrofitting | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Bhagwanpur-II Dev. Block (Av. depth 230 mtr.) = 07 Unit ] Total 07 Unit. | Assistant Engineer, Headquaters |  | ORD/000281/2021-2022 | 1530/TD | 11/01/2022 | 02/03/2022 | MIDNAPUR PIPE CONCERN | 66.72 | 65.61 | 98.33 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | SM/08759 | Retrofitting | Continuation Work Order for Hiring of Diesel Motor Cab/ Luxury Taxy (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.12.2022 to 31.05.2023 i.e. 06 b(Six) months for the use of the office of the Assistant Engineer, RWS Tamluk Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000939/2022-2023 | 375/RWS/TSD | 30/11/2022 | 05/05/2023 | SRIMANTA PANJA | 0.74 | 2.35 | 316.54 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | SM/08759 | Retrofitting | Diesel Motor Cab/Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage IV) on daily rate basis for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, PHE Dte. from 01.07.2023 to 31.12.2023 (Six) Months. | Assistant Engineer |  | ORD/000529/2023-2024 | 1299/TD | 30/06/2023 | 31/12/2023 | JOY MAA TARA TRAVELS & TRANSPORT | 0.87 | 0.37 | 42.47 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Solar Operated Standalone Water Supply Arrangement with Subsequent Functional Household Tap Connection FHTC at different location within Purba Medinipur District under Tamluk Division, PHE Dte. | SM/08759 | Retrofitting | Installation of display Board at 54 nos. different work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000329/2024-2025 | 3288/TD | 05/10/2024 | 25/10/2024 | MISHRA ENTERPRISE | 9 | 0 | 0 | 100
Total | [13 empty] | 423.09 | 392.24 | 92.71