## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Tamluk Division | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Sinking of 300 mm. x 200 mm. dia. x 240 mtr. deep tube well by direct rotary rig method at of 1st Tubewell Site of Shyampur Water Supply Scheme within under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000520/2021-2022 | 1995/TD | 07/03/2022 | 28/03/2022 | AQUATECH ENGINEERS | 15.11 | 0 | 0 | 100
2 | PURBA MEDINIPUR | Moyna | Tamluk Division | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Construction of M.S. Structure over drainage canal to support different dia DI(K-7) distribution pipe & 150 mm dia. DI(K-9) rising main pipe under Shyampur Water Supply Scheme at different Nodal Point within Moyna Block under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte. | Assistant Engineer |  | ORD/000048/2022-2023 | 271/TD | 02/05/2022 | 01/06/2022 | RAJ KUMAR SINGHA | 17.62 | 0 | 0 | 100
3 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Electic quotation bill at Moyna CCC for T/W -I Shyampur Water supply scheme under MMD PHE Dte. |  |  | ORD/000172/2022-2023 | 2003984006/QUOT/1017 | 05/07/2022 | 05/07/2023 | WBSEDCL | 0.56 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Electic quotation bill at Moyna CCC for T/W -II Shyampur Water supply scheme under MMD PHE Dte. |  |  | ORD/000174/2022-2023 | 2003984015/QUOT/1016 | 05/07/2022 | 05/07/2023 | WBSEDCL | 0.56 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. | SM/08878 | New | New Service Connection Full Deposit Scheme, T/W-I of Shyampur Water supply scheme under MMD PHE Dte. |  |  | ORD/000173/2022-2023 | MNA/QUT/22-23/NSC/PHE/201 | 08/07/2022 | 08/07/2023 | WBSEDCL | 1.86 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Moyna | Central Drilling | Shyampur Piped Water Supply Scheme. | SM/08878 | New | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE FOR CONSTRUCTION OF TUBE WELL IN PURBA MEDINIPUR DIST. UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000042/2022-2023 | 241/CMSD-II (D) | 20/05/2022 | 04/06/2022 | MENAKA ENTERPRISE | 2.42 | 0 | 0 | 100
7 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. | SM/08878 | New | New service connection PHE Full deposite scheme for T/W -II of Shyampur Water supply scheme under MMD PHE Dte. |  |  | ORD/000176/2022-2023 | MNA/QUT/22-23/NSC/PHE/101 | 08/07/2022 | 08/07/2023 | WBSEDCL | 1.42 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Moyna | Central Drilling | Shyampur Piped Water Supply Scheme. | SM/08878 | New | PROVIDING TUBE WELL MATERIALS OF 200 MM NOMINAL DIA, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000040/2022-2023 | 244/CMSD-II (D) | 20/05/2022 | 04/06/2022 | MENAKA ENTERPRISE | 3.85 | 0 | 0 | 100
9 | PURBA MEDINIPUR | Moyna | Central Drilling | Shyampur Piped Water Supply Scheme. | SM/08878 | New | SINKING OF 300 MM X 200 MM DIA X 240 MTRS DEPTH TUBE WELL IN PURBA MEDINPUR DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000041/2022-2023 | 242/CMSD-II (D) | 20/05/2022 | 04/06/2022 | MENAKA ENTERPRISE | 3.18 | 0 | 0 | 100
10 | PURBA MEDINIPUR | Moyna | Central Drilling | Shyampur Piped Water Supply Scheme. | SM/08878 | New | PROVIDING TUBE WELL MATERIALS OF 300 MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000043/2022-2023 | 243/ CMSD-II (D) | 20/05/2022 | 04/06/2022 | MENAKA ENTERPRISE | 4.9 | 0 | 0 | 100
11 | PURBA MEDINIPUR | Moyna | Central Drilling | Shyampur Piped Water Supply Scheme. | SM/08878 | New | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000251/2021-2022 | 214/CMSD-I(D) | 09/11/2021 | 24/11/2021 | PADMA ENGINEERING & CO. | 4.52 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. | SM/08878 | New | New Servic Connection Full Deposit Scheme, T/W-I of Shyampur Water supply scheme under MMD PHE Dte. |  |  | VCH/001775/2022-2023 | BP-2022-23-29 | 10/08/2022 | 10/08/2022 | WBSEDCL | 1.86 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Electic quotation bill at Moyna CCC for T/W -II Shyampur Water supply scheme under MMD PHE Dte. |  |  | VCH/001777/2022-2023 | BP-2022-23-30 | 10/08/2022 | 10/08/2022 | WBSEDCL | 0.56 | 0 | 0 | 0
14 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Electic quotation bill at Moyna CCC for Shyampur Water supply scheme under MMD PHE Dte. |  |  | VCH/001776/2022-2023 | BP-2022-23-32 | 11/08/2022 | 11/08/2022 | WBSEDCL | 1.42 | 0 | 0 | 0
15 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Electic quotation bill at Moyna CCC for T/W -I Shyampur Water supply scheme under MMD PHE Dte. |  |  | VCH/001778/2022-2023 | BP-2022-23-28 | 10/08/2022 | 10/08/2022 | WBSEDCL | 0.56 | 0 | 0 | 0
16 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-I under Shyampur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001014/2022-2023 | 1863/W/MMD | 22/09/2022 | 20/01/2023 | PRANAB KUMAR DAS | 12.66 | 0 | 0 | 100
17 | PURBA MEDINIPUR | Moyna | Tamluk Division | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Material Requisition To Resource Division |  |  | RTOR000025/2021-2022 | 1284/TD | 15/12/2021 | 15/12/2021 | Resource Division | 33.3 | 0 | 0 | 0
18 | PURBA MEDINIPUR | Moyna | Tamluk Division | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 1474/TD | 03/01/2022 | 03/01/2022 | Resource Division | 14.11 | 0 | 0 | 0
19 | PURBA MEDINIPUR | Moyna | Tamluk Division | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Material Requisition To Resource Division |  |  | RTOR000033/2021-2022 | 1680/TD | 28/01/2022 | 28/01/2022 | Resource Division | 3.98 | 0 | 0 | 0
20 | PURBA MEDINIPUR | Moyna | Tamluk Division | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 500 Cum and staging height 20.00 mtr. with allied work under Shyampur & its adjoining mouzas Water Supply Scheme within Moyna Dev. Block including supply of all labour & materials under Tamluk sub-division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer |  | ORD/000152/2021-2022 | 1092/TD | 17/11/2021 | 15/06/2022 | RAJ KUMAR SINGHA | 521.85 | 0 | 0 | 100
21 | PURBA MEDINIPUR | Moyna | Tamluk Division | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Interconnection with laying of 150 mm dia DI (K-9) Rising main From 1st & 2nd Tube Well Site to O.H.R. and other allied works at Shyampur PWSS Water Supply Scheme within Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000392/2022-2023 | 1425/TD | 26/09/2022 | 11/10/2022 | MAHAMAYA TIMBER AND CONSTRUCTION | 3.91 | 0 | 0 | 100
22 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Shyampur Piped Water Supply Scheme. | SM/08878 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-II under Shyampur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001130/2022-2023 | 2111/W/MMD | 28/11/2022 | 28/03/2023 | ECO ENTERPRISE | 12.68 | 0 | 0 | 100
Total | [13 empty] | 662.89 | 0 | 0