## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | Baharampur Piped Water Supply Scheme. | SM/08879 | New | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BAHARAMPUR PWSS, BLOCK- BHAGAWANPUR-II UNDER CDD, PHE DTE. |  |  | ORD/000170/2022-2023 | 305/CMSD-I | 08/07/2022 | 23/07/2022 | MENAKA ENTERPRISE | 4.89 | 4.18 | 85.44 | 100
2 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Laying of Distribution pipe line , Construction of Pump House & Boundary Wall, Construction of RCC Over Head Reservoir of Capacity 450 Cum, Sub -Soil Investigation with allied works of Baharampur & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/000151/2021-2022 | 1091/TD | 17/11/2021 | 15/06/2022 | TAPAS SANTRA | 526.12 | 429.67 | 81.67 | 95
3 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Supply & Delivery of 80 mm dia Sluice Valve for Baharampur piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer |  | ORD/000311/2021-2022 | 1687/TD | 31/01/2022 | 15/02/2022 | SANTRA ENTERPRISE. | 4.01 | 4.01 | 100 | 100
4 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Supply & Delivery of 125 mm, 150 mm,200 mm & 250 mm dia Sluice Valve for Baharampur piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer |  | ORD/000312/2021-2022 | 1688/TD | 31/01/2022 | 15/02/2022 | SANTRA ENTERPRISE. | 3.81 | 3.81 | 100 | 100
5 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Construction of Culvert with Wing-wall & Toe wall for Approach Road at 1st TW / Head Work Site ( Mouza- Kalmichhabar ,J.L. No-317, Plot No- 599), for Baharampur Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur,PHE Dte. | Assistant Engineer |  | ORD/000372/2021-2022 | 1682/TD | 28/01/2022 | 14/03/2022 | BIBEKANANDA DAS | 6.41 | 6.4 | 99.96 | 100
6 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Construction of Culvert with Wing-wall & Toe wall for Approach Road at 2nd TW Site ( Mouza- Jethaibari ,J.L. No-307, Plot No- 106), for Baharampur Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur, PHE Dte. | Assistant Engineer |  | ORD/000373/2021-2022 | 1683/TD | 28/01/2022 | 14/03/2022 | BIBEKANANDA DAS | 6.41 | 6.4 | 99.96 | 100
7 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at of 2nd Tubewell Site of Baharampur Water Supply Scheme within under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000513/2021-2022 | 1994/TD | 07/03/2022 | 28/03/2022 | AQUATECH ENGINEERS | 14.76 | 10.39 | 70.39 | 100
8 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Providing Tube Well Materials conforming to IS : 12818:2010 with other works at site for construction of tube well at Baharampur PWSS, Block - Bhagawanpur-II under CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000162/2022-2023 | 305/CMSD-I(D) | 08/07/2022 | 23/07/2022 | MENAKA ENTERPRISE | 4.89 | 0.08 | 1.72 | 100
9 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | Baharampur Piped Water Supply Scheme. | SM/08879 | New | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL & OTHER MATERIALS AT BAHARAMPUR PWSS, BLOCK-BHAGAWANPUR-II BY UTILIZING DEPARTMENTAL MACHINERIES UNDER CDD, PHE DTE. |  |  | ORD/000160/2022-2023 | 303/CMSD-I | 08/07/2022 | 23/07/2022 | MENAKA ENTERPRISE | 3.76 | 1.51 | 40.15 | 100
10 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | Baharampur Piped Water Supply Scheme. | SM/08879 | New | SUPPLY AND DELIVERY OF BRICKS BATS WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BAHARAMPUR PWSS, BLOCK- BHAGAWANPUR-II UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000159/2022-2023 | 246/CMSD-II | 23/05/2022 | 02/06/2022 | MENAKA ENTERPRISE | 0.57 | 0.57 | 100 | 100
11 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | Baharampur Piped Water Supply Scheme. | SM/08879 | New | ADDITIONAL WORKS FOR CONSTRUCTION OF TUBE WELL & OTHER MATERIALS AT SITE FOR BAHARAMPUR PWSS, BLOCK BHAGAWANPUR-II BY UTILIZING SKILLED DRILLING CREW & DEPARTMENTAL MACHINERIES UNDER CDD, PHE DTE. |  |  | ORD/000169/2022-2023 | 304/CMSD-I | 08/07/2022 | 23/07/2022 | MENAKA ENTERPRISE | 4.9 | 3.68 | 75.03 | 100
12 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | Baharampur Piped Water Supply Scheme. | SM/08879 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BAHARAMPUR W/S SCH (TW-I), BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000054/2022-2023 | 380/CDD | 17/05/2022 | 16/06/2022 | MENAKA ENTERPRISE | 14.69 | 5.64 | 38.39 | 100
13 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Electric quotation MADHAKHALI CCC at Baharampur T/W-II Pin-721444 |  |  | VCH/002772/2022-2023 | BP-2022-23-60 | 23/11/2022 | 23/11/2022 | WBSEDCL | 0.61 | 0 | 0 | 0
14 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-2 under Baharampur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001131/2022-2023 | 2112/W/MMD | 28/11/2022 | 28/03/2023 | ALPHA ENTERPRISE | 10.92 | 8.34 | 76.34 | 100
15 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Laying of 150 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials in between 1st Tube well to 2nd Tube Well of Baharampur & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer |  | ORD/000168/2023-2024 | 295/TD | 20/04/2023 | 20/05/2023 | SUBHENDU HAZRA | 3.71 | 2.91 | 78.54 | 100
16 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Supply delivery of Voltage Stabilizer and submersible pump motor set at PH No. II of Baharampur Water Supply Scheme under H.E.S.D. under Midnapore Mechanical Division, P.H.E. Dte. |  | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002188/2022-2023 | 291/MMSD-I | 23/03/2023 | 02/04/2023 | ALPHA ENTERPRISE | 3.06 | 3.06 | 100 | 100
17 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Material Requisition To Resource Division |  |  | RTOR000026/2021-2022 | 1283/TD | 15/12/2021 | 15/12/2021 | Resource Division | 3.37 | 0 | 0 | 0
18 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Material Requisition To Resource Division |  |  | RTOR000030/2021-2022 | 1475/TD | 03/01/2022 | 03/01/2022 | Resource Division | 12.61 | 0 | 0 | 0
19 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 81/TD | 08/04/2022 | 08/04/2022 | Resource Division | 21.16 | 0 | 0 | 0
20 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Electric quotation for Baharampur PWSS Tube Well- I in connection Madhakhali CCC (2004185409) |  |  | BILL/00062/2022-2023 | BP-2022-23-105 | 27/02/2023 | 27/02/2023 | WBSEDCL | 0.47 | 0 | 0 | 0
21 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Retrofitting to accommodate FHTC under JJM in Baharampur PWSS Block - Bhagwanpur-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000715/2023-2024 | 2959/TD | 24/11/2023 | 19/12/2023 | S.D. CONSTRUCTION | 51.79 | 37.96 | 73.3 | 85
22 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | Baharampur Piped Water Supply Scheme. | SM/08879 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Baharampur Piped Water Supply Scheme., Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001342/2022-2023 | 35/W/MMD | 04/01/2023 | 03/07/2023 | SUJOY RANJAN BHOWMICK | 13.58 | 11.58 | 85.24 | 100
Total | [13 empty] | 716.49 | 540.2 | 75.39