## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through trolley mounted PVC tank to different places under Contai-I Block in connection with YAAS for mitigation of Drinking Water crisis under Contai Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District . ( For the period from 01.06.2021 to 21.06.2021 i.e. 21 Days. Total - 8000 litre. | Assistant Engineer | Junior Engineer | ORD/000215/2021-2022 | 82 / CSD | 01/06/2021 | 22/06/2021 | JASODA ENTERPRISE | 1.53 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through trolley mounted PVC tank to different places under Khejuri-II Block in connection with YAAS for mitigation of Drinking Water crisis under Contai Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District . ( For the period from 27.05.2021 to 24.06.2021 i.e. 29 Days. Total - 9000 litre. | Assistant Engineer | Junior Engineer | ORD/000214/2021-2022 | 77 / CSD | 27/05/2021 | 25/06/2021 | GIRI CONSTRUCTION | 2.27 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. ( Part B ) Period from 30.05.21.to 31.05.21 Village - Soula, Habitation - Ramkrishna Misson, G.P - Kalindi | Assistant Engineer |  | ORD/000972/2021-2022 | 83/DSD | 27/05/2021 | 29/05/2021 | SNEHESH SEN | 0.87 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. (From 28/05/21 to14/07/21) Gobindabasan (Padima-II G.P.) | Assistant Engineer |  | ORD/000975/2021-2022 | .84/A/DSD | 27/05/2021 | 14/07/2021 | CHARUBALA ENTERPRISE | 2.43 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 64 days. (From 27/05/21 to 29/07/21) Tangramari-Maity Para , Ghorai Para(Talgachhari-II G.P.) | Assistant Engineer |  | ORD/000959/2021-2022 | 29/Camp/TD | 27/05/2021 | 30/07/2021 | LOKENATH ENTERPRISES | 4.77 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 38 days. (From 27/05/21 to 03/07/21) Biswanathpur- Ghorai Para, Giri Para(Talgachhari-I G.P.) | Assistant Engineer |  | ORD/000961/2021-2022 | 31/Camp/TD | 27/05/2021 | 04/07/2021 | CHARUBALA ENTERPRISE | 3.82 | 0 | 0 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. Period From 29.05.21 to 04.06.21 Village - Mandermoni, Habitation- Sun City Hotel comp, G.P- Kalindi. & Village - Saula, Habitation - Jana Para, G.P- Kalindi. | Assistant Engineer | Junior Engineer | ORD/000973/2021-2022 | 83/A/DSD | 27/05/2021 | 03/06/2021 | SOM CONSTRUCTION | 1.43 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. ( Part B ) Village - Dadanpatrabar, Habitation - Patra Para, Sau Para under kalindi GP, Village - Purba Purusattampur, Habitation - Das Para, Patra Para under Kalindi GP, Village - Dakshin Purusattampur, Habitation - Nayek Para, Maity Para, under Kalindi GP. | Assistant Engineer | Junior Engineer | ORD/000951/2021-2022 | 21/Camp/TD | 27/05/2021 | 14/07/2021 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.22 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. Village - Alampur (Balisai GP), Village - Dublabari (Talgachhari - II GP) for the period of 58 days. (From 27/05/21 to 23/07/21). | Assistant Engineer |  | ORD/000953/2021-2022 | 23/Camp/TD | 27/05/2021 | 24/07/2021 | ANUPAM CONSTRUCTION | 4.35 | 0 | 0 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. ( Part A ) Village - karanjee, Habitation - Giri Para, Patra Para, Sau Para under Balisai GP, Village - Mandarmoni, Habitation - Near Police Camp, Sun City under Kalindi GP. | Assistant Engineer | Junior Engineer | ORD/000952/2021-2022 | 22/Camp/TD | 27/05/2021 | 14/07/2021 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.82 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. Tajpur(Talgachhari-II G.P.) | Assistant Engineer |  | ORD/000954/2021-2022 | 24/Camp/TD | 27/05/2021 | 14/07/2021 | DHANANJOY DAS | 3.9 | 0 | 0 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. Chandpur(Talgachhari-II G.P.) & Jaldah(Talgachhari-II G.P.) For the Period of 49 days. (From 27/05/21 to14/07/21) | Assistant Engineer |  | ORD/000955/2021-2022 | 25/Camp/TD | 27/05/2021 | 15/07/2021 | DHANANJOY DAS | 4.84 | 0 | 0 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 49 days. (From 27/05/21 to14/07/21) Kshirpal(Talgachhari-II G.P.) & Bherichauli(Talgachhari-II G.P.) | Assistant Engineer |  | ORD/000957/2021-2022 | 27/Camp/TD | 27/05/2021 | 15/07/2021 | SNEHESH SEN | 4.84 | 0 | 0 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 49 days. (From 27/05/21 to14/07/21) Jamra Shyampur- Kar Para(Talgachhari-II G.P.) & Dolboldia-Bamun Para, Das Para(Talgachhari-II G.P.) | Assistant Engineer |  | ORD/000967/2021-2022 | 37/Camp/TD | 27/05/2021 | 14/07/2021 | MAITY CONSTRUCTION | 4.84 | 0 | 0 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 63 days. (From 27/05/21 to28/07/21) .Kaima(Talgachhari-II G.P.) | Assistant Engineer |  | ORD/000958/2021-2022 | 28/Camp/TD | 27/05/2021 | 29/07/2021 | LOKENATH ENTERPRISES | 3.14 | 0 | 0 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-II Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District.( Part A ) Village - Saula, Habitation - Aila Center, Jana para, Mandal para, G.P - Kalindi & Village - Arakbonia, Habitation - Patra para, Sau Para, G.P - Kalindi Period From 29.05.21 to 16.07.21 | Assistant Engineer | Junior Engineer | ORD/000970/2021-2022 | 40/Camp/TD | 27/05/2021 | 15/07/2021 | SOM CONSTRUCTION | 4.09 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-II Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District.( Part B ) Village - Saula, Habitation - Ramkrishna Mission G.P - Kalindi, Village - Andaman, Habitation - Bar Para, Das Para, G.P - Kalindi & Village - Sonamoy, Habitation - Mandal Para, Maity Para, G.P - Kalindi Period From 29.05.21 to 16.07.21 | Assistant Engineer | Junior Engineer | ORD/000971/2021-2022 | 41/Camp/TD | 27/05/2021 | 15/07/2021 | SOM CONSTRUCTION | 4.09 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 65 days. (From 27/05/21 to 30/07/21) Bodhra(Talgachhari-II G.P.) | Assistant Engineer |  | ORD/000960/2021-2022 | 30/Camp/TD | 27/05/2021 | 30/07/2021 | LOKENATH ENTERPRISES | 4.22 | 0 | 0 | 100
19 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 64 days. (From 27/05/21 to 29/07/21) Biswanathpur- Das Para, Mitra Para(Talgachhari-I G.P.) | Assistant Engineer |  | ORD/000962/2021-2022 | 32/Camp/TD | 27/05/2021 | 30/07/2021 | CHARUBALA ENTERPRISE | 4.77 | 0 | 0 | 100
20 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 48 days. (From 27/05/21 to13/07/21) Biswanathpur- Chanda Para, Mondal Para(Talgachhari-I G.P.) | Assistant Engineer |  | ORD/000963/2021-2022 | 33/Camp/TD | 27/05/2021 | 14/07/2021 | BASANTA KUMAR MAITY | 4.75 | 0 | 0 | 100
21 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 49 days. (From 28/05/21 to15/07/21) Jashipur- Patrapara, Das Para, Nayak Para(Talgachhari-II G.P.) | Assistant Engineer |  | ORD/000965/2021-2022 | 35/Camp/TD | 27/05/2021 | 14/07/2021 | MAITY CONSTRUCTION | 4.84 | 0 | 0 | 100
22 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 49 days. (From 27/05/21 to 14/07/21) Panchdoria(Talgachhari-II G.P.) & Sankarpur(Talgachhari-II G.P.) | Assistant Engineer |  | ORD/000966/2021-2022 | 36/Camp/TD | 27/05/2021 | 14/07/2021 | MAITY CONSTRUCTION | 4.84 | 0 | 0 | 100
23 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 54 (Fifty Four) days. (From 27/05/21 to 21/07/21) Jamra Shyampur-Jana Para,Bar Para,Bamun Par(Talgachhari-II G.P.) | Assistant Engineer |  | ORD/000968/2021-2022 | 38/Camp/TD | 27/05/2021 | 20/07/2021 | DAS ENTERPRISE. | 4.21 | 0 | 0 | 100
24 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Work Order for Supply of safe Drinking water through trolley mounted PVC tank to Bhekutia Gram Panchayat at 5th part Jalpai location under Nandigram-I Block in connection with YASS for mitigation of Drinking water crisis under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. (for the period from 02.06.2021 to 30.06.2021 i.e. 29 Days) | Assistant Engineer | Junior Engineer | ORD/001001/2021-2022 | 99/B/HSD | 01/06/2021 | 30/06/2021 | RAJ KUMAR SINGHA | 0.84 | 0 | 0 | 0
25 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 49 days. (From 28/05/21 to15/07/21) | Assistant Engineer |  | ORD/000956/2021-2022 | 26/Camp/TD | 27/05/2021 | 15/07/2021 | SNEHESH SEN | 4.84 | 0 | 0 | 100
26 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 54 (Fifty Four) days. (From 27/05/21 to 21/07/21) Jamra Shyampur-Bera Para,Khatua Para(Talgachhari-II G.P.) & Jamra Shyampur-Saupara(Talgachhari-II G.P.) | Assistant Engineer |  | ORD/000969/2021-2022 | 39/Camp/TD | 27/05/2021 | 20/07/2021 | DAS ENTERPRISE. | 4.84 | 0 | 0 | 100
27 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Supply of Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. For the Period of 61 days. (From 26/05/21 to 25/07/21) Aila Center(Talgachhari-II G.P.) | Assistant Engineer |  | ORD/000974/2021-2022 | 84/DSD | 27/05/2021 | 27/07/2021 | KAMAL KUMAR ROY | 1.52 | 0 | 0 | 100
28 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. ( Part A ) | Assistant Engineer |  | ORD/001009/2021-2022 | 356/TD | 16/07/2021 | 30/07/2021 | MAITY CONSTRUCTION | 4.54 | 0 | 0 | 100
29 | PURBA MEDINIPUR |  | Tamluk Division | Supply of safe drinking water through Trolley Mounted PVC tank at different villages within different block to mitigate acute crisis of drinking water on the situation of YAAS effected area under Tamluk Division, PHE Dte in Purba Medinipur District (Part- | SM/08985 | Disaster | Safe Drinking Water through Trolley Mounted PVC Tank to different Villages over "YAAS" affected Area Within Ramnagar-I Block for mitigation of drinking water crisis under Digha Sub-Division of Tamluk Division, PHE Dte. in Purba Medinipur District. ( Part B ) | Assistant Engineer |  | ORD/001010/2021-2022 | 357/TD | 16/07/2021 | 30/07/2021 | BASANTA KUMAR MAITY | 4.54 | 0 | 0 | 100
Total | [13 empty] | 108.02 | 0 | 0