## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Khejuri-II, Egra-I, Egra-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000760/2023-2024 | 2977/TD | 29/11/2023 | 29/12/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Ramnagar-I, Ramnagar-II, Patashpur-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days | Assistant Engineer, Headquaters |  | ORD/000761/2023-2024 | 2965/TD | 28/11/2023 | 28/12/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Contai-I, Contai-II (Deshapran), Contai-III Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000762/2023-2024 | 3027/TD | 29/11/2023 | 29/12/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 3.02 | 64.08 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Chandipur, Moyna, Nandakumar Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000763/2023-2024 | 2951/TD | 24/11/2023 | 24/12/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Nandigram-I, Nandigram-II, Patashpur-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000764/2023-2024 | 3028/TD | 29/11/2023 | 29/12/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Haldia, Mahishadal, Sutahata Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000765/2023-2024 | 2952/TD | 24/11/2023 | 24/12/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Tamluk Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000766/2023-2024 | 2934/TD | 23/11/2023 | 23/12/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 3.39 | 3.39 | 100 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Kolaghat, Panskura, Sahid Matangini Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000758/2023-2024 | 2976/TD | 29/11/2023 | 29/12/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Bhagwanpur -I , Bhagwanpur -II, Khejuri-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/12/2023 to 02/01/2024 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000759/2023-2024 | 2964/TD | 28/11/2023 | 28/12/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Kolaghat, Panskura, Sahid Matangini Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | Assistant Engineer, Headquaters |  | ORD/000621/2023-2024 | 2176/TD | 01/09/2023 | 01/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.52 | 95.83 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Bhagwanpur -I , Bhagwanpur -II, Khejuri-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | Assistant Engineer, Headquaters |  | ORD/000622/2023-2024 | 2177/TD | 01/09/2023 | 01/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.33 | 91.67 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Khejuri-II, Egra-I, Egra-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | Assistant Engineer, Headquaters |  | ORD/000623/2023-2024 | 2178/TD | 01/09/2023 | 01/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.03 | 85.42 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Tamluk Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | Assistant Engineer, Headquaters |  | ORD/000663/2023-2024 | 2182-A/TD | 01/09/2023 | 01/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 3.39 | 3.39 | 100 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Contai-I, Contai-II (Deshapran), Contai-III Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | Assistant Engineer, Headquaters |  | ORD/000659/2023-2024 | 2180/TD | 01/09/2023 | 01/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.36 | 92.5 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Ramnagar-I, Ramnagar-II, Patashpur-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | Assistant Engineer, Headquaters |  | ORD/000658/2023-2024 | 2179/TD | 01/09/2023 | 01/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.62 | 97.92 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Chandipur, Moyna, Nandakumar Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | Assistant Engineer, Headquaters |  | ORD/000660/2023-2024 | 2181/TD | 01/09/2023 | 01/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Haldia, Mahishadal, Sutahata Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | Assistant Engineer, Headquaters |  | ORD/000662/2023-2024 | 2182/TD | 01/09/2023 | 01/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Kolaghat, Panskura, Sahid Matangini Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000667/2023-2024 | 2517/TD | 29/09/2023 | 29/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
19 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Chandipur, Moyna, Nandakumar Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000691/2023-2024 | 2724/TD | 31/10/2023 | 30/11/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
20 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Nandigram-I, Nandigram-II, Patashpur-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/09/2023 to 02/10/2023 i.e. 01 month. | Assistant Engineer, Headquaters |  | ORD/000661/2023-2024 | 2181-A/TD | 01/09/2023 | 01/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.52 | 95.83 | 100
21 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Kolaghat, Panskura, Sahid Matangini Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000684/2023-2024 | 2719/TD | 31/10/2023 | 30/11/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
22 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Contai-I, Contai-II (Deshapran), Contai-III Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000690/2023-2024 | 2723/TD | 31/10/2023 | 30/11/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 1.69 | 35.92 | 100
23 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Khejuri-II, Egra-I, Egra-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000687/2023-2024 | 2721/TD | 31/10/2023 | 30/11/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
24 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Tamluk Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000695/2023-2024 | 2727/TD | 31/10/2023 | 30/11/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 3.39 | 3.39 | 100 | 100
25 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Nandigram-I, Nandigram-II, Patashpur-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000692/2023-2024 | 2725/TD | 31/10/2023 | 30/11/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
26 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Contai-I, Contai-II (Deshapran), Contai-III Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000671/2023-2024 | 2517-D/TD | 29/09/2023 | 29/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
27 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Nandigram-I, Nandigram-II, Patashpur-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000673/2023-2024 | 2518-A/TD | 29/09/2023 | 29/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
28 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Chandipur, Moyna, Nandakumar Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000672/2023-2024 | 2518/TD | 29/09/2023 | 29/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 3.02 | 64.06 | 100
29 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Bhagwanpur -I , Bhagwanpur -II, Khejuri-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000668/2023-2024 | 2517-A/TD | 29/09/2023 | 29/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
30 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Khejuri-II, Egra-I, Egra-II Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000669/2023-2024 | 2517-B/TD | 29/09/2023 | 29/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100.01 | 100
31 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Tamluk Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000675/2023-2024 | 2518-C/TD | 29/09/2023 | 29/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 3.39 | 3.39 | 100 | 100
32 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Ramnagar-I, Ramnagar-II, Patashpur-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days | Assistant Engineer, Headquaters |  | ORD/000670/2023-2024 | 2517-C/TD | 29/09/2023 | 29/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
33 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Haldia, Mahishadal, Sutahata Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 03/10/2023 to 01/11/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000674/2023-2024 | 2518-B/TD | 29/09/2023 | 29/10/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 99.99 | 100
34 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Haldia, Mahishadal, Sutahata Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000693/2023-2024 | 2726/TD | 31/10/2023 | 30/11/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
35 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Bhagwanpur -I , Bhagwanpur -II, Khejuri-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days. | Assistant Engineer, Headquaters |  | ORD/000685/2023-2024 | 2720/TD | 31/10/2023 | 30/11/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
36 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Continuation for Engagement of Implementation Support Agency (ISA) in the Ramnagar-I, Ramnagar-II, Patashpur-I Block of Purba Medinipur district in connection with Jal Jeevan Mission for the period of 02/11/2023 to 01/12/2023 i.e. 30 days | Assistant Engineer, Headquaters |  | ORD/000689/2023-2024 | 2722/TD | 31/10/2023 | 30/11/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
37 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Haldia, Mahishadal, Sutahata Block of Purba Medimipur district in connection with Jal Jeevan Mission. | Assistant Engineer, Headquaters |  | ORD/000556/2023-2024 | 1785-H/TD | 03/08/2023 | 02/09/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
38 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Khejuri-II, Egra-I, Egra-II Block of Purba Medimipur district in connection with Jal Jeevan Mission. | Assistant Engineer, Headquaters |  | ORD/000551/2023-2024 | 1785-C/TD | 03/08/2023 | 02/09/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
39 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Chandipur, Moyna, Nandakumar Block of Purba Medimipur district in connection with Jal Jeevan Mission. | Assistant Engineer, Headquaters |  | ORD/000554/2023-2024 | 1785-F/TD | 03/08/2023 | 02/09/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
40 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Contai - I, Contai-II(Deshpran), Contai-III Block of Purba Medimipur district in connection with Jal Jeevan Mission. | Assistant Engineer, Headquaters |  | ORD/000553/2023-2024 | 1785-E/TD | 03/08/2023 | 02/09/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
41 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Kolaghat, Panskura, Sahid Matangini Block of Purba Medimipur district in connection with Jal Jeevan Mission. | Assistant Engineer, Headquaters |  | ORD/000549/2023-2024 | 1785-A/TD | 03/08/2023 | 02/09/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
42 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Bhagwanpur -I , Bhagwanpur -II, Khejuri-I Block of Purba Medimipur district in connection with Jal Jeevan Mission. | Assistant Engineer, Headquaters |  | ORD/000550/2023-2024 | 1785-B/TD | 03/08/2023 | 02/09/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
43 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Ramnagar-I, Ramnagar - II, Patashpur -I Block of Purba Medimipur district in connection with Jal Jeevan Mission. | Assistant Engineer, Headquaters |  | ORD/000552/2023-2024 | 1785-D/TD | 03/08/2023 | 02/09/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
44 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Nandigram-I, Nandigram - II, Patashpur-II Block of Purba Medimipur district in connection with Jal Jeevan Mission. | Assistant Engineer, Headquaters |  | ORD/000555/2023-2024 | 1785-G/TD | 03/08/2023 | 02/09/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 4.72 | 4.72 | 100 | 100
45 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) in the Tamluk Block of Purba Medimipur district in connection with Jal Jeevan Mission. | Assistant Engineer, Headquaters |  | ORD/000557/2023-2024 | 1785-I/TD | 03/08/2023 | 02/09/2023 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 3.39 | 3.39 | 100 | 100
46 | PURBA MEDINIPUR |  | Tamluk Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Medinipur District. | SM/09022 | Support-M&E | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building support activities at Purba Medinipore district Under Jal Jeevan Mission (JJM) under Tamluk Division, PHE Dte. (For 12 months) | Assistant Engineer | Junior Engineer | ORD/000833/2023-2024 | 3327/TD | 27/12/2023 | 21/12/2024 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 536.61 | 88.68 | 16.53 | 50
Total | [13 empty] | 742.3 | 286.03 | 38.53