## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Basudebberya Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000176/2021-2022 | 1185/TD | 02/12/2021 | 22/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 12.84 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Supply & Delivery of different dia. Sluice Valve for Augmentation of Basudebberia Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/000126/2022-2023 | 630/TD | 23/06/2022 | 08/07/2022 | BIBEKANANDA DAS | 4.82 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 260MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR Basudebberya W/S SCH (TW-I), DESHPRAN BLOCK UNDER PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000247/2022-2023 | 1344/CDD | 24/11/2022 | 24/12/2022 | MENAKA ENTERPRISE | 19.77 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Basudebbrya, JL No. 428 Plot No. 2879) of Basudebberya Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000101/2022-2023 | 477/TD | 03/06/2022 | 24/06/2022 | TAPAS KUMAR GIRI | 17.91 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya in Block - Deshopran under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001449/2022-2023 | 159/W/MMD | 02/02/2023 | 01/08/2023 | MUKHERJEE ART CENTRE | 25.26 | 0 | 0 | 54
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Supply and Delivery of Different dia Sluice Valves for Basudebberiya Water Supply Scheme in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000887/2022-2023 | 440 / CSD | 20/03/2023 | 04/04/2023 | GIRI ENTERPRISE | 0.91 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2021-2022 | 1252/TD | 13/12/2021 | 13/12/2021 | Resource Division | 19.67 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2021-2022 | 1953/TD | 04/03/2022 | 04/03/2022 | Resource Division | 16.73 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Laying distribution pipe line and providing of FHTC for Augmentation of Basudebberiya Water Supply Scheme In Deshpran Block in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000471/2021-2022 | 1946/TD | 03/03/2022 | 30/08/2022 | M/S A.R. ENTERPRISE | 490.93 | 0 | 0 | 90
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Laying distribution pipe line & Accommodate FHTC (60 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - E) | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 541/TD | 12/05/2023 | 01/10/2024 | GRAND CONSTRUCTION | 9.36 | 0 | 0 | 60
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Relaying of Existing Damaged Distribution Pipe Line With allied Works for Augmentation Of Basudebberiya Water Supply Scheme in Deshpran Block Of Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000333/2023-2024 | 807/TD | 30/05/2023 | 29/06/2023 | A-PLUS | 20.92 | 0 | 0 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Basudebbrya, JL No. 428 Plot No. 2879) of Basudebberya Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tubewell Site (Mouza- Uttar Ektarpur, JL No. - 136, Plot No. 38) of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000562/2023-2024 | 2048/TD | 25/08/2023 | 04/10/2023 | KALPANA BUILDERS | 34.03 | 0 | 0 | 40
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Quotation for new service connection at TW-III of Basudebberia ws scheme under MMD,PHE Dte, Block-Contai-III, Marishda CCC Application no-2004765941 Con ID-204324592 |  |  | BILL/00592/2024-2025 | BP-2024-25-290 | 29/07/2024 | 29/07/2024 | WBSEDCL | 6.15 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Laying of Washout pipeline, Repairing of OHR, Pump House no 1, Pump House No. 2 and Head Works Boundary Wall under JJM with allied work of Basudebberiya PWSS within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000292/2024-2025 | 3057/TD | 19/09/2024 | 24/10/2025 | ABHIJIT BERA | 19.56 | 0 | 0 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya | SM/09034 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Basudebberiya Water Supply Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). |  |  | ORD/000636/2024-2025 | 849/TD | 19/03/2025 | 18/05/2025 | SMMD | 3.59 | 0 | 0 | 0
Total | [13 empty] | 702.45 | 0 | 0