## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS under Contai II (Deshapran) Block (Phase-II). | SM/09048 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS Block - Contai-II in the District of Purba Medinipur. Mouza- Sofiabad(497),Dholmari(498),Kultalia(500),(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000129/2021-2022 | 1009/TD | 02/11/2021 | 02/12/2021 | RELIABLE CONSTRUCTIONS | 35.54 | 35.66 | 100.33 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS under Contai II (Deshapran) Block (Phase-II). | SM/09048 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000056/2024-2025 | 2162/TD | 05/07/2024 | 05/07/2024 | Resource Division | 0.81 | 0 | 0 | 0
Total | [13 empty] | 36.35 | 35.66 | 98.09