## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Mandarmani PWSS (Phase-II) under Ramnagar II Block | SM/09052 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Mandarmani PWSS (PHASE-II) Block - Ramnagar-II in the District of Purba Medinipur. (PART- A) | Assistant Engineer | Junior Engineer | ORD/000137/2021-2022 | 1019/TD | 02/11/2021 | 22/11/2021 | ABHIJIT BERA | 21.29 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Mandarmani PWSS (Phase-II) under Ramnagar II Block | SM/09052 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Mandarmani PWSS (PHASE-II) Block - Ramnagar-II in the District of Purba Medinipur ( PART - B ) | Assistant Engineer | Junior Engineer | ORD/000138/2021-2022 | 1020/TD | 02/11/2021 | 02/12/2021 | UNIQUE AGENCY | 52.71 | 0 | 0 | 100
Total | [13 empty] | 74.01 | 0 | 0