## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Chirulia PWSS under Egra II Block (Phase-II) | SM/09054 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Chirulia PWSS Block - Egra-II in the District of Purba Medinipur. (PHASE- II) | Assistant Engineer | Junior Engineer | ORD/000132/2021-2022 | 1014/TD | 02/11/2021 | 02/12/2021 | FIROZ KHAN | 44.75 | 43.55 | 97.31 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Chirulia PWSS under Egra II Block (Phase-II) | SM/09054 | Retrofitting | Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000594/2023-2024 | 2209/TD | 01/09/2023 | 31/10/2023 | MISHRA ENTERPRISE | 9.53 | 3 | 31.47 | 100
Total | [13 empty] | 54.28 | 46.55 | 85.75