## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Basudevpur PWSS under Egra II Block (Phase-II) | SM/09055 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Basudevpur ( Phase-II ) PWSS Block-Egra-II in the District Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000131/2021-2022 | 1013/TD | 02/11/2021 | 02/12/2021 | SNEHESH SEN | 69.11 | 67.16 | 97.18 | 100
Total | [13 empty] | 69.11 | 67.16 | 97.18