## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) | SM/09056 | Retrofitting | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- D) | Assistant Engineer | Junior Engineer | ORD/000136/2021-2022 | 1018/TD | 02/11/2021 | 22/11/2021 | NARAYAN CHANDRA DAS | 22.37 | 22.37 | 99.99 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) | SM/09056 | Retrofitting | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- A) | Assistant Engineer | Junior Engineer | ORD/000133/2021-2022 | 1015/TD | 02/11/2021 | 22/11/2021 | MAA KALI CONSTRUCTION | 20.35 | 18.99 | 93.35 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) | SM/09056 | Retrofitting | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- B) | Assistant Engineer | Junior Engineer | ORD/000134/2021-2022 | 1016/TD | 02/11/2021 | 22/11/2021 | LOKENATH ENTERPRISES | 20.29 | 20.28 | 99.99 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) | SM/09056 | Retrofitting | Laying ( Left out ) UPVC pipe line to accommodate FHTC under JJM in PANCHROL PWSS within EGRA -I BLOCK ( to Support phase I FHTC ) (part -B )under Digha Sub Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000285/2021-2022 | 1541/TD | 11/01/2022 | 26/01/2022 | LOKENATH ENTERPRISES | 4.76 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) | SM/09056 | Retrofitting | Laying distribution pipe line to accommodate FHTC of Panchrol Water Supply Scheme within Egra - I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. Within (Panchrol West part ). | Assistant Engineer | Junior Engineer | ORD/000348/2021-2022 | 1781/TD | 08/02/2022 | 28/02/2022 | SHAKEEL KHAN | 11.26 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Retorfitting to accommodate FHTC under JJM in Panchrol PWSS under Egra I Block (Phase-I) | SM/09056 | Retrofitting | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- C) | Assistant Engineer | Junior Engineer | ORD/000135/2021-2022 | 1017/TD | 02/11/2021 | 22/11/2021 | SHAKEEL KHAN | 22.37 | 22.37 | 100 | 100
Total | [13 empty] | 101.38 | 84.01 | 82.87