## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Balance Work for Retrofitting to Accommodate FHTC (300 nos) and Laying of Left-Out Portion UPVC Pipeline due to uncovered area of different Nodal point of Srirampur and its Adjoining Mouzas Water Supply Scheme under JJM within Tamluk Block under Tamluk S | SM/09073 | Retrofitting | Retrofitting to accommodate FHTC (300 Nos.) under JJM in Srirampur PWSS (PART-I) Block - Tamluk in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000154/2021-2022 | 1125/TD | 22/11/2021 | 01/01/2022 | GHOSH ENTERPRISE | 19.58 | 0 | 0 | 100
Total | [13 empty] | 19.58 | 0 | 0