## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Manikpur PWSS and Jalpai Part-II PWSS under Nandigram-I and II Dev. Block. | SM/09074 | Retrofitting | Retrofitting to accommodate FHTC (335 Nos.) under JJM in Manikpur PWSS & Jalpai Part-II PWSS (Balance Part) Block -Nandigram-I & Nandigram-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000153/2021-2022 | 1124/TD | 22/11/2021 | 12/12/2021 | SANKHA ENTERPRISE | 36.47 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accommodate FHTC under JJM in Manikpur PWSS and Jalpai Part-II PWSS under Nandigram-I and II Dev. Block. | SM/09074 | Retrofitting | Work order for laying of left out HDPE pipe line at Manikpur & Champainagar mouja for Manikpur & its Adjoining Mouzas W/S Scheme within Nandigram - I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000297/2022-2023 | 599/HSD | 30/08/2022 | 09/09/2022 | SANKHA ENTERPRISE | 2.46 | 0 | 0 | 100
Total | [13 empty] | 38.92 | 0 | 0