## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09272 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Mechogram Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000181/2021-2022 | 1190/TD | 02/12/2021 | 22/12/2021 | INDRANIL DUTTA & ASSOCIATES | 5.28 | 5.28 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09272 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 1256/TD | 13/12/2021 | 13/12/2021 | Resource Division | 0.59 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09272 | Augmentation | Rejuvenation of Dakshin Mechogram Water Supply Scheme by Providing Laying Distribution System and FHTC in Panskura Block in the District of Purba Medinipur. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000307/2021-2022 | 1668/TD | 25/01/2022 | 25/05/2022 | M/S. CHANDI CHARAN MISHRA & CO. | 134.86 | 123.22 | 91.37 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09272 | Augmentation | Rejuvenation of Dakshin Mechogram Water Supply Scheme by Providing Laying Distribution System and FHTC in Panskura Block in the District of Purba Medinipur. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000306/2021-2022 | 1667/TD | 25/01/2022 | 25/05/2022 | SWADHIN KUMAR CHAKRABORTY | 135.54 | 135.32 | 99.84 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09272 | Augmentation | Laying distribution system of pipe line and its allied works for Dakshin Mechogram & its adjoining mouzas Water Supply Scheme at Panskura-I Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000306/2022-2023 | 1146/TD | 31/08/2022 | 20/09/2022 | M/S. CHANDI CHARAN MISHRA & CO. | 14.56 | 14.4 | 98.92 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09272 | Augmentation | Supply of sluice valve & delivery at Chapbasan Store for Dakshin Mechogram PWSS within Panskura-I Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000091/2022-2023 | 442/TD | 31/05/2022 | 15/06/2022 | SWADHIN KUMAR CHAKRABORTY | 3.34 | 3.34 | 100 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09272 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2021-2022 | 1730/TD | 02/02/2022 | 02/02/2022 | Resource Division | 12.11 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09272 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 419/TD | 25/05/2022 | 25/05/2022 | Resource Division | 1.16 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09272 | Augmentation | 1(One) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room, Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Dakshin Mechogram Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000130/2023-2024 | 267/TD | 20/04/2023 | 04/06/2023 | TARUN KHATUA | 13.06 | 12.52 | 95.89 | 96
10 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09272 | Augmentation | Augmentation Of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura-I Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000734/2022-2023 | 2552/TD | 24/01/2023 | 25/03/2023 | FARID UDDIN AHMED | 43.27 | 25.35 | 58.58 | 100
Total | [13 empty] | 363.77 | 319.43 | 87.81