## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District | SM/09273 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chatra Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000180/2021-2022 | 1189/TD | 02/12/2021 | 22/12/2021 | INDRANIL DUTTA & ASSOCIATES | 3.53 | 3.53 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District | SM/09273 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Rejuvenation of Chatra Water Supply Scheme in Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer | Junior Engineer | ORD/000535/2023-2024 | 1836/TD | 08/08/2023 | 28/08/2023 | RAMESH & SHANTI ENGINEERING WORKS | 3.13 | 3.13 | 100 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District | SM/09273 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2021-2022 | 1731/TD | 02/02/2022 | 02/02/2022 | Resource Division | 8.76 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District | SM/09273 | Augmentation | Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division ,PHE Dte. Under Tamluk Division for the period from 12 (Twelve) Months. | Assistant Engineer |  | ORD/000619/2022-2023 | 1345/TSD | 28/10/2022 | 24/06/2023 | TAPAS SANTRA | 1.14 | 2.39 | 210.35 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District | SM/09273 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000212/2023-2024 | 1112/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District | SM/09273 | Augmentation | Rejuvenation of Ground Water Based Chatra PWSS by Providing Laying Distribution System and FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000302/2021-2022 | 1648/TD | 20/01/2022 | 20/04/2022 | MAITY ENTERPRISE | 165.08 | 51.25 | 31.05 | 70
7 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation and Retrofitting of Ground Water Based Chatra PWSS to accommodate FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District | SM/09273 | Augmentation | Repairing and Renovation of the Elevated Water Reservoir, Renovation of Switch Room cum Chlorine Room with water supply & sanitary arrangement at 2nd. T/W Site Along with Renovation of Existing Boundary Wall and Renovation of Switch Room cum Chlorine Room with sanitary arrangement at 1st. Tube well site i.c.w Rejuvenation of Ground Water Based Chatra PWSS by Providing Laying Distribution System and FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000336/2024-2025 | 3335/TD | 22/10/2024 | 01/01/2026 | TAPAS SANTRA | 14.99 | 0 | 0 | 100
Total | [13 empty] | 196.81 | 60.3 | 30.64