## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | SM/09274 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000173/2021-2022 | 1182/TD | 02/12/2021 | 22/12/2021 | HORIZEN | 2.94 | 2.94 | 100 | 100
2 | PURBA MEDINIPUR |  | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | SM/09274 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TW BY DEPARTMENTAL RIG MACHINE IN RAMNAGAR-II BLOCK, UNDER CDD,PHE DTE. |  |  | ORD/000089/2022-2023 | 183/CMSD-I(D) | 10/06/2022 | 25/06/2022 | PADMA ENGINEERING & CO. | 4.92 | 4.66 | 94.65 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | SM/09274 | Augmentation | PROVIDING TW MATERIALS CONFORMING TO 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TW AT RAMNAGAR-II BLOCK, UNDER CMSD-I(D), CDD,PHE DTE. |  |  | ORD/000090/2022-2023 | 184/CMSD-I(D) | 10/06/2022 | 25/06/2022 | PADMA ENGINEERING & CO. | 5 | 4.97 | 99.37 | 100
4 | PURBA MEDINIPUR |  | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | SM/09274 | Augmentation | PROVIDING PEA SIZE GRAVELS AND OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TW AT RAMNAGAR-II BLOCK, UNDER CMSD-I(D), CDD,PHE DTE. |  |  | ORD/000091/2022-2023 | 185/CMSD-I(D) | 10/06/2022 | 25/06/2022 | PADMA ENGINEERING & CO. | 5 | 3.13 | 62.63 | 100
5 | PURBA MEDINIPUR |  | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | SM/09274 | Augmentation | ADDITIONAL CARRIAGE OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT MADAR PWSS (T/W-III), BLOCK - RAMNAGAR-II UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000134/2022-2023 | 352/CMSD-I (D) | 26/07/2022 | 05/08/2022 | PADMA ENGINEERING & CO. | 0.16 | 0.16 | 100 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | SM/09274 | Augmentation | Augmentation of ground water based Mandar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 150 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Ramnagar-II Dev. Block under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000376/2021-2022 | 1813/TD | 11/02/2022 | 10/08/2022 | BASANTA KUMAR MAITY | 199.91 | 122.57 | 61.31 | 70
7 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | SM/09274 | Augmentation | Supply of C.I D.F Sluice valve for Augmentation of ground water based Mander W/S Scheme to accommodate FHTC within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000212/2022-2023 | 324/DSD | 15/07/2022 | 22/07/2022 | BASANTA KUMAR MAITY | 2.86 | 2.86 | 100 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | SM/09274 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 1261/TD | 13/12/2021 | 13/12/2021 | Resource Division | 5.63 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | SM/09274 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2021-2022 | 1869/TD | 17/02/2022 | 17/02/2022 | Resource Division | 5.31 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | SM/09274 | Augmentation | Quotation money payment to WBSEDCL for Mandar Water Supply Scheme of Tube Well No. - III |  |  | BILL/00468/2023-2024 | BP-2023-24-237 | 09/08/2023 | 09/08/2023 | WBSEDCL | 3.54 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | SM/09274 | Augmentation | Laying of Distribution pipe line, Rising main pipe line, Pump House, Boundary Wall, Sinking of 3rd Tube Well with allied works of Mandar & its adjoining mouzas Water Supply Scheme within RAMNAGAR -II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000114/2023-2024 | 244/TD | 19/04/2023 | 03/06/2023 | BASANTA KUMAR MAITY | 59.1 | 28.91 | 48.92 | 50
12 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | SM/09274 | Augmentation | Valve operator (one no) in head work site at Mandar & its adjoining mouzas water supply scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division PHE Dte. (From 01.10.2024 to 03.04.2025 i.e. 185 days) | Assistant Engineer |  | ORD/000517/2024-2025 | 1026/DSD | 01/10/2024 | 04/04/2025 | DAS ENTERPRISE. | 1.2 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. | SM/09274 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000054/2023-2024 | 1220/W/MMD | 25/04/2023 | 19/04/2024 | S.G.TECHNICAL SERVICE | 11.96 | 0 | 0 | 100
Total | [13 empty] | 307.54 | 170.2 | 55.34