## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. | SM/09275 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Muradpur Water Supply Scheme under Tamluk Division, PHE Dte. |  | Junior Engineer | ORD/000187/2021-2022 | 1196/TD | 02/12/2021 | 22/12/2021 | INDRANIL DUTTA & ASSOCIATES | 6.38 | 6.38 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. | SM/09275 | Augmentation | Rejuvenation & Retrofitting of ground water based Muradpur PWSS & its adjoining moujas within Chandipur Dev. Block under Tamluk sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. (Part-A) |  | Junior Engineer | ORD/000631/2021-2022 | 2214/TD | 22/03/2022 | 20/06/2022 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 237.6 | 236 | 99.33 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. | SM/09275 | Augmentation | Rejuvenation & Retrofitting of ground water based Muradpur PWSS & its adjoining moujas within Chandipur Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000005/2022-2023 | 59/TD | 05/04/2022 | 04/06/2022 | UCON | 164.31 | 161.84 | 98.5 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. | SM/09275 | Augmentation | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS & its adjoining moujas with in Chandipur Dev. Block under Tamluk Sub-Division , PHE Dte. Dist. Purba Medinipur (Part-A) |  | Junior Engineer | ORD/000423/2022-2023 | 1597/TD | 18/10/2022 | 17/11/2022 | G. S. CONSTRUCTION | 25.21 | 24.82 | 98.43 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. | SM/09275 | Augmentation | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS & its adjoining moujas with in Chandipur Dev. Block under Tamluk Sub-Division , PHE Dte. Dist. Purba Medinipur (Part-B) |  | Junior Engineer | ORD/000424/2022-2023 | 1598/TD | 18/10/2022 | 12/11/2022 | TARUN KHATUA | 10.28 | 10.16 | 98.92 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. | SM/09275 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2021-2022 | 2346/TD | 31/03/2022 | 31/03/2022 | Resource Division | 10.33 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. | SM/09275 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 1096/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur. | SM/09275 | Augmentation | Pilling with Bamboo & bullah, retaining of OHR & laying leftout portion for Muradpur PWSS & its adjoining moujas with in Chandipur Dev. Block under Tamluk Sub Division of Tamluk Division, PHE Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000453/2023-2024 | 1471/TD | 13/07/2023 | 22/08/2023 | G. S. CONSTRUCTION | 34.18 | 0 | 0 | 50
Total | [13 empty] | 488.48 | 439.21 | 89.91