## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09277 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Rasikachak Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000185/2021-2022 | 1194/TD | 02/12/2021 | 22/12/2021 | INDRANIL DUTTA & ASSOCIATES | 4.62 | 4.62 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09277 | Augmentation | Piling work and pond crossing of Rejuvenation & Retrofitting of ground water based Rashikachak PWSS & its adjoining mouzas within Chandipur Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000659/2022-2023 | 2344/TD | 10/01/2023 | 04/02/2023 | JAGANNATH MAKAR | 29.39 | 28.47 | 96.89 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09277 | Augmentation | Rejuvenation & Retrofitting of ground water based Rashikachak PWSS & its adjoining moujas within Chandipur Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000090/2022-2023 | 432/TD | 27/05/2022 | 25/08/2022 | JAGANNATH MAKAR | 234.25 | 229.76 | 98.09 | 95
4 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09277 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000195/2023-2024 | 1095/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09277 | Augmentation | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. |  |  | ORD/000243/2024-2025 | 2695/TD | 22/08/2024 | 21/09/2024 | HARIPADA PATTANAYAK | 38.26 | 0 | 0 | 0
Total | [13 empty] | 306.7 | 262.85 | 85.7