## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000172/2021-2022 | 1181/TD | 02/12/2021 | 22/12/2021 | HORIZEN | 6.91 | 5.92 | 85.72 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 1260/TD | 13/12/2021 | 13/12/2021 | Resource Division | 21.19 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Augmentation of ground water based Kalindi Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 450 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Ramnagar-II Dev. Block under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000605/2021-2022 | 2185/TD | 17/03/2022 | 13/09/2022 | BASANTA KUMAR MAITY | 533.41 | 376.04 | 70.5 | 50
4 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Supply of 80 mm.dia C.I D.F sluice valve for laying distribution & rising main pipe line of Kalindi W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000371/2022-2023 | 1049/TD | 17/08/2022 | 24/08/2022 | BASANTA KUMAR MAITY | 4.72 | 4.72 | 100 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Supply & delevary of 100 mm,200mm,150mm & 250mm dia C.I D.F sluice valve for laying distribution & rising main pipe line of Kalindi W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000445/2022-2023 | 1155/TD | 31/08/2022 | 07/09/2022 | BASANTA KUMAR MAITY | 4.28 | 4.28 | 100 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Supply of 125 mm.dia C.I D.F sluice valve for laying distribution & rising main pipe line of Kalindi W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000211/2022-2023 | 323/DSD | 15/07/2022 | 22/07/2022 | BASANTA KUMAR MAITY | 1.32 | 1.32 | 100 | 100
7 | PURBA MEDINIPUR |  | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Resistivity Survey and other works of Kalindi WS Scheme (TW-Il) , Ramnagar-ll Block under Purba Midnapore District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000512/2022-2023 | 1540/CDD | 08/12/2022 | 01/04/2024 | MENAKA ENTERPRISE | 12.67 | 9.92 | 78.34 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2021-2022 | 2348/TD | 31/03/2022 | 31/03/2022 | Resource Division | 16.82 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Laying Rising Main Pipe Line With allied Works For Augmentation Of KALINDI Water Supply Scheme In Ramnagar-II Block Of Purba Medinipur District | Assistant Engineer | Junior Engineer | ORD/000872/2022-2023 | 3223/TD | 14/03/2023 | 03/04/2023 | ABHIJIT BERA | 6.86 | 6.34 | 92.48 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Laying of Distribution pipe line by UPVC pipes with allied works for complete balance FHTC under Kalindi & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000468/2023-2024 | 1449/TD | 13/07/2023 | 12/08/2023 | BASANTA KUMAR MAITY | 24.44 | 23.58 | 96.5 | 100
11 | PURBA MEDINIPUR |  | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 240 mtrs. Depth) by utilising Departmental machineries for Kalindi W/S Scheme(TW-I), Ramnagar-II block under Purba medinipur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000016/2023-2024 | 857/CDD | 10/07/2023 | 09/08/2023 | MENAKA ENTERPRISE | 18.74 | 14.63 | 78.05 | 100
12 | PURBA MEDINIPUR |  | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Providing drilling crews Including Allied Materials for construction of Tube Well at Kalindi within Ramnagar-II Block, District Purba Medinipur under Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000125/2023-2024 | 1536/CDD | 06/10/2023 | 03/04/2024 | MENAKA ENTERPRISE | 8.73 | 5.11 | 58.53 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Renovation & Repairing of existing pump house I & II, Boundary Wall at head works & 2nd tube well site of Kalindi Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000372/2024-2025 | 3401/TD | 28/10/2024 | 07/12/2024 | DAS ENTERPRISE. | 9.65 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme. | SM/09278 | Augmentation | Repairing of Existing pipe line with allied works for non functional to functional FHTC under Kalindi & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. |  | Junior Engineer | ORD/000042/2025-2026 | 42/DSD | 11/04/2025 | 18/04/2025 | ABHIJIT BERA | 0.97 | 0 | 0 | 100
Total | [13 empty] | 670.69 | 451.86 | 67.37