## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09279 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Paramanandapur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000184/2021-2022 | 1193/TD | 02/12/2021 | 22/12/2021 | INDRANIL DUTTA & ASSOCIATES | 4.74 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09279 | Augmentation | Augmentation of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000727/2022-2023 | 2557/TD | 24/01/2023 | 25/03/2023 | M/S. S. A. CONSTRUCTION | 41.95 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09279 | Augmentation | Rejuvenation & Retrofitting of ground water based Paramanandapur PWSS to accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (Part- B) | Assistant Engineer | Junior Engineer | ORD/000169/2022-2023 | 743/TD | 05/07/2022 | 03/09/2022 | SATYABRATA BHAUMIK | 165 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09279 | Augmentation | Proposed Rejuvenation &Retrofitting of Laying Distribution System of proposed left out portion pipe line at Paramanandapur PWSS | Assistant Engineer | Junior Engineer | ORD/000830/2022-2023 | 3170/TD | 10/03/2023 | 30/03/2023 | PURNA CHANDRA BARH | 7.63 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09279 | Augmentation | Rejuvenation & Retrofitting of ground water based Paramanandapur PWSS to accommodate FHTC in Moyna Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part- A) | Assistant Engineer | Junior Engineer | ORD/000006/2022-2023 | 58/TD | 05/04/2022 | 04/06/2022 | BARH CONSTRUCTION | 130.82 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/09279 | Augmentation | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room,Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Paramanandapur Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000173/2023-2024 | 330/TD | 25/04/2023 | 14/07/2025 | SUDIP MANNA | 13.09 | 0 | 0 | 100
Total | [13 empty] | 363.21 | 0 | 0