## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. | SM/09280 | Augmentation | Rejuvenation & Retrofitting of ground water based Haur PWSS & its adjoining moujas within Panskura Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000038/2022-2023 | 137/TD | 19/04/2022 | 18/07/2022 | ASIS KUMAR SARANGI | 192.27 | 114.53 | 59.57 | 90
2 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. | SM/09280 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Haur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000182/2021-2022 | 1191/TD | 02/12/2021 | 22/12/2021 | INDRANIL DUTTA & ASSOCIATES | 5.95 | 5.95 | 100 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. | SM/09280 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2021-2022 | 2343/TD | 31/03/2022 | 31/03/2022 | Resource Division | 11.07 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. | SM/09280 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000211/2023-2024 | 1111/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. | SM/09280 | Augmentation | Rejuvenation & Retrofitting of ground water based Haur PWSS & its adjoining moujas within Panskura Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000010/2022-2023 | 53/TD | 05/04/2022 | 04/06/2022 | MUNNA AGROTECH ENTERPRISE | 150.85 | 99.71 | 66.1 | 90
6 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. | SM/09280 | Augmentation | Proposed Left out portion of pipe line Rejuvenation & Retrofitting of of HAUR PWSS under Tamluk Sub Division, PHE Dte. (PART- B) | Assistant Engineer | Junior Engineer | ORD/000295/2024-2025 | 3064/TD | 19/09/2024 | 14/10/2024 | KAMALA ENTERPRISE | 14.42 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground water Based Haur PWSS to Accommodate FHTC in Panskura Block Under Tamluk Division in Purba Medinipur District. | SM/09280 | Augmentation | Construction of Boundary Wall ( 1mtr height) & Painting Pump House and Boundary wall & other allied works at 1 st TW site, Dismantling of Existing B/W & Construction of Boundary Wall with Gate and along PCC road & other allied works at 2nd TW site of Haur Pipe Water Supply Scheme, within Panskura-I Block under Tamluk Sadar Sub-Division of Tamluk Division, PHE Dte. |  |  | ORD/000632/2024-2025 | 736/TD | 07/03/2025 | 16/04/2025 | SINHA BUILDERS | 9.71 | 0 | 0 | 0
Total | [13 empty] | 384.45 | 220.19 | 57.27