## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000161/2021-2022 | 1165/TD | 01/12/2021 | 08/12/2021 | HORIZEN | 5.74 | 5.61 | 97.78 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | Augmentation | Supply & delivery of different dia CIDF Sluice valve for Rajarampur Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000106/2022-2023 | 514/TD | 07/06/2022 | 27/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.81 | 4.81 | 100 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | Augmentation | Supply & delivery of different dia CIDF Sluice valve for Rajarampur Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000107/2022-2023 | 515/TD | 07/06/2022 | 27/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.7 | 3.7 | 100 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | Augmentation | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Kapaseria W/S Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head work Site of Rajarampur W/S Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Tabakhali W/S Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000235/2022-2023 | 976/TD | 03/08/2022 | 24/08/2022 | SIMPLEX DRILLING COMPANY | 58.06 | 19.28 | 33.2 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | Augmentation | Work Order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2022 to 31/12/2022. (12 Months) | Assistant Engineer | Junior Engineer | ORD/001005/2021-2022 | 476/HSD | 27/12/2021 | 27/12/2022 | SUSANTA PATTANAYAK | 1.5 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | Augmentation | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Rajarampur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000256/2022-2023 | 1069/TD | 22/08/2022 | 06/10/2022 | TAPAN BERA | 3.96 | 3.93 | 99.39 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 1253/TD | 13/12/2021 | 13/12/2021 | Resource Division | 40.29 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 465/W | 02/06/2022 | 02/06/2022 | Resource Division | 55.01 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2021-2022 | 2344/TD | 31/03/2022 | 31/03/2022 | Resource Division | 16.03 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | Augmentation | Restoration work of the damaged flank portions caused for laying pipe line by PHE Dte.on Rautari to Terapara Jalpai road from Ch.8.5 KM to 9.85 KM under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 |  |  | BILL/00237/2023-2024 | BP-2023-24-122 | 14/06/2023 | 14/06/2023 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 5.76 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | Augmentation | Crossing permission of laying HDPE pipeline along and across of NH-116 of Rajarampur Water Supply Scheme under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000819/2023-2024 | 3289/TD | 20/12/2023 | 09/01/2024 | DONA ASSOCIATES | 8.69 | 1.22 | 14.04 | 25
12 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | Augmentation | Augmentation of ground water based Rajarampur Water Supply Scheme by Providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 400 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.. | Assistant Engineer | Junior Engineer | ORD/000528/2021-2022 | 2021/TD | 08/03/2022 | 01/11/2025 | SANKHA ENTERPRISE | 549.46 | 437.5 | 79.62 | 90
13 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Function Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme. | SM/09281 | Augmentation | Laying Rising main, laying left out pipe line and supporting work with Drum Sheet walling and Earth filling in Rajarampur Water Supply Scheme within Mahishadal Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000549/2022-2023 | 2167/TD | 19/12/2022 | 03/03/2026 | SANKHA ENTERPRISE | 78.54 | 23.06 | 29.37 | 35
Total | [13 empty] | 831.52 | 499.11 | 60.02