## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000158/2021-2022 | 1162/TD | 01/12/2021 | 08/12/2021 | HORIZEN | 7.18 | 7.16 | 99.79 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 533 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Bhandarberya) (PART-E) | Assistant Engineer | Junior Engineer | ORD/000342/2021-2022 | 1775/TD | 08/02/2022 | 10/03/2022 | S.D. CONSTRUCTION | 58 | 32.49 | 56.01 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 586 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Ganapatinagar) (PART-K) | Assistant Engineer | Junior Engineer | ORD/000346/2021-2022 | 1779/TD | 08/02/2022 | 20/03/2022 | BHOLANATH DEY | 57.93 | 47 | 81.12 | 95
4 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 388 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-II) (PART-D) | Assistant Engineer | Junior Engineer | ORD/000341/2021-2022 | 1774/TD | 08/02/2022 | 10/03/2022 | ADHIKARY CONSTRUCTION | 42.02 | 31.98 | 76.11 | 95
5 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 810 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-I) (PART-C) | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000340/2021-2022 | 1773/TD | 08/02/2022 | 03/06/2026 | NARAYAN MANDAL | 74.62 | 68.32 | 91.56 | 95
6 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 510 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Nimtouri,P-I) (PART-F) | Assistant Engineer | Junior Engineer | ORD/000343/2021-2022 | 1776/TD | 08/02/2022 | 20/03/2022 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 76.98 | 67.75 | 88.01 | 95
7 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 858 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Chak Srikrishnapur &Uttar Narikelda) (PART-H) | Assistant Engineer | Junior Engineer | ORD/000344/2021-2022 | 1777/TD | 08/02/2022 | 20/03/2022 | NARAYAN CHANDRA DAS | 86.75 | 81.26 | 93.68 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 484 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme''(Mouza-Payrachali) (PART-J) | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000345/2021-2022 | 1778/TD | 08/02/2022 | 10/09/2026 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 43.68 | 39.07 | 89.45 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 204 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Nimtouri,P-II) (PART-G) | Assistant Engineer | Junior Engineer | ORD/000588/2021-2022 | 2061/TD | 15/03/2022 | 14/04/2022 | J.M. CONSTRUCTION | 29.04 | 24.61 | 84.74 | 95
10 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Uttar Sonamui Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000557/2022-2023 | 2215/TD | 22/12/2022 | 16/01/2023 | ADHIKARY CONSTRUCTION | 4.46 | 3.93 | 87.98 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Uttar Sonamui Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000556/2022-2023 | 2214/TD | 22/12/2022 | 16/01/2023 | KRISHNENDU SEKHAR DAS | 4.56 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Different works for providing functional house hold tap connection (FHTC 374 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Kulberya) (PART-I) | Assistant Engineer | Junior Engineer | ORD/000589/2021-2022 | 2062/TD | 15/03/2022 | 14/04/2022 | SK. NUR ISLAM | 51.1 | 48.35 | 94.62 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 2nd Tube well Site of Uttar Sonamui Water Supply Scheme within Tamluk Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000219/2022-2023 | 905/TD | 27/07/2022 | 17/08/2022 | AQUATECH ENGINEER | 17.25 | 15.53 | 90.05 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Uttar Sonamui Water Supply Scheme within Tamluk Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000218/2022-2023 | 904/TD | 27/07/2022 | 17/08/2022 | AQUATECH ENGINEER | 17.25 | 15.84 | 91.79 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Left-out portion of uncovered area with uPVC pipe line and its allied works for Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-II) within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(PART-B) | Assistant Engineer | Junior Engineer | ORD/000230/2022-2023 | 971/TD | 03/08/2022 | 18/08/2022 | KRISHNENDU SEKHAR DAS | 8.3 | 8.29 | 99.93 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Supply & Delivery of different dia DI Specials for Laying of Distribution Main (K-7) of Different works for providing functional house hold tap connection(FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/000331/2022-2023 | 1175/TSD | 09/09/2022 | 24/09/2022 | SK. NUR ISLAM | 1.92 | 1.77 | 92.05 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Left-out portion of uncovered area with uPVC pipe line and its allied works for Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-I) within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(PART-A) | Assistant Engineer | Junior Engineer | ORD/000229/2022-2023 | 970/TD | 03/08/2022 | 18/08/2022 | NARAYAN MANDAL | 10.6 | 10.59 | 99.91 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2021-2022 | 1833/TD | 15/02/2022 | 15/02/2022 | Resource Division | 26.06 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000083/2021-2022 | 2191/TD | 21/03/2022 | 21/03/2022 | Resource Division | 30.92 | 0 | 0 | 0
20 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Interconnection with laying of 150 mm dia DI(K-9) Rising main From 3 rd Tube Well & 2 nd Tube Well Site to O.H.R. Site and other allied works at Uttar Sonamui Water Supply Scheme within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000842/2022-2023 | 3196/TD | 14/03/2023 | 29/03/2023 | MAHAMAYA TIMBER AND CONSTRUCTION | 5.48 | 0 | 0 | 0
21 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Sutahata and Tamluk in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000053/2023-2024 | 1218/W/MMD | 25/04/2023 | 22/10/2023 | BHABANI PRASAD MANNA | 40.43 | 23.84 | 58.96 | 60
22 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Construction of R.C.C. Elevated Reservoir of capacity 450 cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Uttar Sonamui & its adjoining moujas Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District . (PART-A) | Assistant Engineer | Junior Engiener | ORD/000745/2022-2023 | 2550/TD | 24/01/2023 | 31/01/2025 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 149.76 | 120.36 | 80.37 | 80
23 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room for Water Supply (as per Deptt. drawing) at 2nd. Tube well site. of Uttar Sonamui Pipe Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte.in the District of Purba Medinipur . | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engiener | ORD/000731/2023-2024 | 2982/TD | 29/11/2023 | 13/01/2024 | KRISHNENDU SEKHAR DAS | 7.81 | 4.3 | 55.01 | 100
24 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Payment to WBSEDCL for Quotation Money of Uttar Sonamui PWSS under Tamluk Division, PHE Dte. |  |  | BILL/00015/2023-2024 | BP-2023-24-1 | 13/04/2023 | 13/04/2023 | WBSEDCL | 0.5 | 0 | 0 | 0
25 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Payment to WBSEDCL for Quotation Money for Uttar Sonamui PWSS under Tamluk Division, PHE Dte. |  |  | BILL/00645/2022-2023 | BP-2022-23-934 | 30/03/2023 | 30/03/2023 | WBSEDCL | 4.34 | 0 | 0 | 0
26 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Leftout FHTC- 15 Nos. including supplying, laying, fitting, fixing of Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials and labour for Uttar Sonamui Water Supply Scheme under Uttar Sonamui Gram Panchayat Area within Tamluk-II Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. in the District of Purba Medinipur . | Assistant Engineer | Junior Engiener | ORD/000200/2024-2025 | 1061/TSD | 19/07/2024 | 11/10/2024 | DIPANKAR MALAKAR | 0.97 | 0.72 | 74.66 | 100
27 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | SM/09282 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000222/2023-2024 | 1121/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
Total | [13 empty] | 858.1 | 653.16 | 76.12