## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | SEALING OF SALINE ZONEAT SITE FOR CONSTRUCTION OF TUBE WELL AT RANGIBASAN W/S SCHEME (TW-III), MAHISHADAL BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000224/2022-2023 | 454/CMSD-I | 01/09/2022 | 08/09/2022 | MENAKA ENTERPRISE | 0.47 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000171/2021-2022 | 1180/TD | 02/12/2021 | 22/12/2021 | HORIZEN | 5.56 | 5.56 | 100 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 280 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR RANGIBASAN W/S SCHEME (TW-III), MAHISBADAL BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000111/2022-2023 | 109/CDD | 12/04/2022 | 12/05/2022 | MENAKA ENTERPRISE | 18.7 | 17.85 | 95.44 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Work Order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2022 to 31/12/2022. (12 Months) | Assistant Engineer | Junior Engineer | ORD/001006/2021-2022 | 476/HSD, | 27/12/2021 | 27/12/2022 | SANTANU PATTANAYAK | 1.5 | 1.91 | 127.43 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Rangibasan Water Supply Scheme under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000389/2023-2024 | 1053/TD | 07/06/2023 | 27/06/2023 | MA SARADA ENTERPRISE | 0.73 | 0.73 | 100 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Rangibasan Water Supply Scheme under Haldia Sub-Division of Tamluk Division in Purba Medinipur District (PART-A) | Assistant Engineer | Junior Engineer | ORD/000388/2023-2024 | 1052/TD | 07/06/2023 | 27/06/2023 | SSPR VALVE MANUFACTURING PVT. LTD. | 5.9 | 5.9 | 100 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 1258/TD | 13/12/2021 | 13/12/2021 | Resource Division | 11.32 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2021-2022 | 1867/TD | 17/02/2022 | 17/02/2022 | Resource Division | 19.09 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Electric Quotation Bill for Rangibasan PWSS |  |  | BILL/00226/2022-2023 | BP-2022-23-637 | 20/01/2023 | 20/01/2023 | WBSEDCL | 0.59 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Restoration work of the damaged flank portions caused for laying pipe line by PHE Dte.on Mahishadal-Geonkhali road from Ch.0.20 km to 1.10 km under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 |  |  | BILL/00235/2023-2024 | BP-2023-24-120 | 14/06/2023 | 14/06/2023 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.98 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well site of Rangibasan Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000459/2023-2024 | 1496/TD | 17/07/2023 | 31/08/2023 | PULAK KUMAR SAMANTA | 4.81 | 4.6 | 95.78 | 60
12 | PURBA MEDINIPUR |  | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 240 Mtrs. Depth) by utilising Departmental Machineries for Solat/Rangibasan W/S Scheme (T/W-II) , under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000196/2023-2024 | 858/CDD | 10/07/2023 | 30/07/2024 | PADMA ENGINEERING & CO. | 18.74 | 17.81 | 95.05 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Sinking of 300 mm x 200 mm dia x 280 mtr. deep tube well by direct rotary rig method at 3rd Tubewell site of Rangibasan Water Supply Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000846/2023-2024 | 51/TD | 04/01/2024 | 18/02/2024 | AQUATECH ENGINEER | 20.68 | 19.69 | 95.21 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Repairing & Renovation of Switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube Well site of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000655/2023-2024 | 2620/TD | 11/10/2023 | 10/11/2023 | PULAK KUMAR SAMANTA | 5.98 | 0 | 0 | 3
15 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Laying Distribution System of Leftout portion, Providing Functional Household Tap Connection (FHTC) of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000143/2024-2025 | 2013/TD | 14/06/2024 | 23/04/2025 | A. R. CONSTRUCTION | 56.76 | 0 | 0 | 20
16 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000054/2025-2026 | 417/HSD, | 23/04/2025 | 03/05/2025 | ANIRBAN BHOWMIK | 0.94 | 0 | 0 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- C) | Assistant Engineer | Junior Engineer | ORD/000055/2025-2026 | 418/HSD, | 23/04/2025 | 03/05/2025 | BHOWMIK ENTERPRISE | 0.97 | 0 | 0 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- D) | Assistant Engineer | Junior Engineer | ORD/000056/2025-2026 | 419/HSD, | 23/04/2025 | 03/05/2025 | ANIRBAN BHOWMIK | 0.96 | 0 | 0 | 100
19 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- F) | Assistant Engineer | Junior Engineer | ORD/000058/2025-2026 | 421/HSD, | 23/04/2025 | 03/05/2025 | ANIRBAN BHOWMIK | 0.97 | 0 | 0 | 100
20 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/000053/2025-2026 | 416/HSD, | 23/04/2025 | 03/05/2025 | ANIRBAN BHOWMIK | 0.97 | 0 | 0 | 100
21 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- E) | Assistant Engineer | Junior Engineer | ORD/000057/2025-2026 | 420/HSD, | 23/04/2025 | 03/05/2025 | ANIRBAN BHOWMIK | 0.97 | 0 | 0 | 100
22 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division |  |  | BILL/00701/2025-2026 |  | 20/08/2025 | 20/08/2025 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.96 | 0 | 0 | 0
23 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Augmentation of ground water based Rangibasan Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 450 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000375/2021-2022 | 1814/TD | 11/02/2022 | 30/07/2025 | DAS CONSTRUCTION | 481.17 | 376.05 | 78.15 | 65
24 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Laying of supply & delivery of different dia D.I specials for Rising main line and inter connection at Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000463/2023-2024 | 1493/TD | 17/07/2023 | 28/12/2025 | S.D. CONSTRUCTION | 7.32 | 1.95 | 26.6 | 10
25 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme. | SM/09283 | Augmentation | Renovation of Boundary Wall and land development at Head Work Site of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Length - 212.00 Mtr.) | Assistant Engineer | Junior Engineer | ORD/000244/2024-2025 | 2693/TD | 22/08/2024 | 17/08/2025 | BHOWMIK & SONS | 21.73 | 0 | 0 | 30
Total | [13 empty] | 690.76 | 452.04 | 65.44