## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenkua Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000160/2021-2022 | 1164/TD | 01/12/2021 | 08/12/2021 | HORIZEN | 5.92 | 5.83 | 98.48 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 1255/TD | 13/12/2021 | 13/12/2021 | Resource Division | 12.45 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Supply & delivery of different dia CIDF Sluice Valve for Dhenkua Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte.(Part-B) | Assistant Engineer | Junior Engineer | ORD/000070/2022-2023 | 347/TD | 13/05/2022 | 02/06/2022 | TAPAS SANTRA | 3.67 | 3.67 | 100 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Supply & delivery of different dia CIDF Sluice Valve for Dhenkua Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte.(PART-A) | Assistant Engineer | Junior Engineer | ORD/000069/2022-2023 | 346/TD | 13/05/2022 | 02/06/2022 | TAPAS SANTRA | 4.49 | 4.49 | 100 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Augmentation of ground water based Dhenkua Water Supply Scheme by Providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 400 cum and staging height 20.00 mtr. With allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000007/2022-2023 | 57/TD | 05/04/2022 | 02/10/2022 | RAJ KUMAR SINGHA | 563.22 | 508.91 | 90.36 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | G.I pipe column with M.S. Structure for laying of D.I pipe line & HDPE pipe line with Casing at Dhenkua Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. (Total Length= 65.00 mtr, {i) NP-116 to 46= 20mt + ii) NP-90 to 5= 2.5mt + iii) NP 10 to 11 = 2.5 Mtr. + iv) NP - 199 to 168 = 20.0mt + NP - 151 to 154 =20.0mtr.} | Assistant Engineer | Junior Engineer | ORD/000233/2022-2023 | 974/TD | 03/08/2022 | 23/08/2022 | RAJ KUMAR SINGHA | 9.49 | 4.79 | 50.49 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Laying Rising main and supporting work with Drum Sheet walling and Earth filling in Dhenkua Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000234/2022-2023 | 975/TD | 03/08/2022 | 25/12/2024 | RAJ KUMAR SINGHA | 87.92 | 79.54 | 90.47 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well site of Dhenkua Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000299/2022-2023 | 1133/TD | 30/08/2022 | 28/11/2022 | DIPANKAR MALAKAR | 4.75 | 2.74 | 57.57 | 100
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well No I under Dhenkua water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001139/2022-2023 | 2120/W/MMD | 28/11/2022 | 28/03/2023 | DIPALI CONSTRUCTION | 11.1 | 10.95 | 98.62 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2021-2022 | 2345/TD | 31/03/2022 | 31/03/2022 | Resource Division | 15.83 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Central Drilling | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Dhenuka W/S Scheme (T/W-II), Sutahata Block under Purba Midnapur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000126/2023-2024 | 877/CDD | 11/07/2023 | 03/07/2024 | MENAKA ENTERPRISE | 21.16 | 19.85 | 93.8 | 100
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Electric Quotation for Denkua Water Supply SchemeT/W-I (Ref. ID-224005066 ) |  |  | BILL/01617/2023-2024 | BP-2023-24-135 | 20/07/2023 | 20/07/2023 | WBSEDCL | 0.11 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Laying of Left-out portion Distribution pipe line and Household Tap Connection (FHTC) for Dhenkua Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000134/2024-2025 | 3466/TD | 06/11/2024 | 10/02/2025 | RAJ KUMAR SINGHA | 54.66 | 0 | 0 | 70
14 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Dhenkua Water supply scheme, Sutahata block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000389/2024-2025 | 2005/W/MMD | 30/08/2024 | 26/02/2025 | P.K.ENGINEERING | 9.29 | 0 | 0 | 80
15 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenuka Water Supply Scheme | SM/09284 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000125/2024-2025 | 802/TD | 18/03/2025 | 18/03/2025 | Resource Division | 5.54 | 0 | 0 | 0
Total | [13 empty] | 809.61 | 640.77 | 79.15