## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | SM/09285 | Augmentation | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Begunberia Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000122/2021-2022 | 1000/TD | 01/11/2021 | 21/11/2021 | SAYAN MAITY | 4.25 | 3.26 | 76.68 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | SM/09285 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000174/2021-2022 | 1183/TD | 02/12/2021 | 22/12/2021 | HORIZEN | 7 | 7 | 100 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | SM/09285 | Augmentation | Supply & delivery of different dia CIDF Sluice valve of Begunberia Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000072/2022-2023 | 355/TD | 13/05/2022 | 02/06/2022 | SANTRA ENTERPRISE. | 4.85 | 4.85 | 100 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | SM/09285 | Augmentation | Supply & delivery of different dia CIDF Sluice valve of Begunberia Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000073/2022-2023 | 356/TD | 13/05/2022 | 02/06/2022 | SANTRA ENTERPRISE. | 4.42 | 4.42 | 100 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | SM/09285 | Augmentation | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Begunberia Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000033/2022-2023 | 132/TD | 19/04/2022 | 10/05/2022 | SIMPLEX DRILLING COMPANY | 19.03 | 19.03 | 100 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | SM/09285 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2021-2022 | 1257/TD | 13/12/2021 | 13/12/2021 | Resource Division | 71.92 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | SM/09285 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2021-2022 | 2347/TD | 31/03/2022 | 31/03/2022 | Resource Division | 25.41 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | SM/09285 | Augmentation | Payment to WBSEDCL for Electric Quotation money of Begunberia Tube Well No. ¿ III |  |  | BILL/00378/2023-2024 | BP-2023-24-206 | 25/07/2023 | 25/07/2023 | WBSEDCL | 0.56 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | SM/09285 | Augmentation | Restoration work of the damaged flank portions caused for laying pipe line by PHE Dte.on Terapara Jalpai to Jaganathpur (Basulia Hospital to Horikhali) road from Ch.0.42 KM to 2.00 KM under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 |  |  | BILL/00238/2023-2024 | BP-2023-24-123 | 14/06/2023 | 14/06/2023 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.68 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | SM/09285 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Sutahata and Tamluk in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000053/2023-2024 | 1218/W/MMD | 25/04/2023 | 22/10/2023 | BHABANI PRASAD MANNA | 40.43 | 12.76 | 31.56 | 60
11 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | SM/09285 | Augmentation | Construction of boundary wall, Retaining wall, Approach road & Earth filling Work in 3rd tubewell site of Begunberia Water Supply scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) , (length of Retaining wall-16mtr) & (length of Approach road-10mtr). | Assistant Engineer | Junior Engineer | ORD/000573/2023-2024 | 2162/TD | 31/08/2023 | 30/09/2023 | M/S SOURAV MAHAPATRA | 22.85 | 16.96 | 74.22 | 20
12 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme. | SM/09285 | Augmentation | Augmentation of ground water based Begunberia Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 600 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000636/2021-2022 | 2335/TD | 29/03/2022 | 01/10/2025 | TAPAS SANTRA | 681.46 | 590.71 | 86.68 | 92
Total | [13 empty] | 886.86 | 658.99 | 74.31