## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | Augmentation | Laying distribution pipe line, and providing of FHTC for Rejuvenation of GOBINDANAGAR & its adjoining moujas Water Supply Scheme within Panskura Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000409/2021-2022 | 1899/TD | 23/02/2022 | 22/08/2022 | TARUN KOLEY | 554.16 | 397.79 | 71.78 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Gobindanagar (Zone-I & Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000183/2021-2022 | 1192/TD | 02/12/2021 | 22/12/2021 | INDRANIL DUTTA & ASSOCIATES | 9.26 | 9.26 | 100 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | Augmentation | Charges for entry of Household data in J.J.M. website along with House hold Addhar detai1s and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. The work should be taken up as per direction of Engineer-In-Charge. N.B. This item should be exclusively used for IMIS entry through J.J.M. | Assistant Engineer | Junior Engineer | ORD/000029/2022-2023 | 90/TD | 11/04/2022 | 11/05/2022 | MISHRA ENTERPRISE | 4.85 | 4.85 | 100 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | Augmentation | Supply of sluice valve & delivery at Chapbasan Store for Gobindanagar Zone-I & II PWSS within Panskura-I Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-A) | Assistant Engineer | Junior Engineer | ORD/000088/2022-2023 | 424/TD | 27/05/2022 | 11/06/2022 | TARUN KOLEY | 4.32 | 4.32 | 100 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | Augmentation | Supply of sluice valve & delivery at Chapbasan Store for Gobindanagar Zone-I & II PWSS within Panskura-I Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-B) | Assistant Engineer | Junior Engineer | ORD/000089/2022-2023 | 425/TD | 27/05/2022 | 11/06/2022 | TARUN KOLEY | 3.65 | 3.65 | 100 | 100
6 | PURBA MEDINIPUR |  | Central Drilling | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR GOBINDANAGAR W/S SCH (ZONE-I, TW-III), PANSKURA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000410/2022-2023 | 2119/CDD | 02/03/2023 | 01/04/2023 | PADMA ENGINEERING & CO. | 17.76 | 15.08 | 84.94 | 0
7 | PURBA MEDINIPUR |  | Central Drilling | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | Augmentation | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 230 mtrs. depth) by utilising Departmental machineries for Gobindanagar W/S Scheme (Z-II) panskura block under purba medinipur district, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000426/2022-2023 | 2112/CDD | 02/03/2023 | 01/04/2023 | PADMA ENGINEERING & CO. | 17.76 | 13.68 | 77.04 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | Augmentation | Quotation money payment to WBSEDCL for GobindanagarZone-II Water Supply Scheme of Tube Well No. - IV |  |  | BILL/00599/2023-2024 | BP-2023-24-324 | 29/08/2023 |  | WBSEDCL | 4.39 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | Augmentation | Land development and making approach road of 3 (three) nos. Boosting Tube Well site at Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000729/2023-2024 | 2980/TD | 29/11/2023 | 19/12/2023 | M/S. S. A. CONSTRUCTION | 5.11 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 1259/TD | 13/12/2021 |  | Resource Division | 4.42 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 417/TD | 25/05/2022 |  | Resource Division | 2.19 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2021-2022 | 1954/TD | 04/03/2022 |  | Resource Division | 23.84 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Rejuvenation & Retrofitting of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. (Zone - I & Zone- II) | SM/09286 | Augmentation | Augmentation of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura-I Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 2558/TD | 24/01/2023 | 25/03/2023 | TARUN KOLEY | 73.36 | 45.81 | 62.44 | 100
Total | [13 empty] | 725.05 | 494.43 | 68.19