## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sapai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000178/2021-2022 | 1187/TD | 02/12/2021 | 22/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.13 | 4.11 | 80.23 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 1251/TD | 13/12/2021 | 13/12/2021 | Resource Division | 0.35 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including land development for Additional Tube Well at J.L. No.-171, PLot no.-65/215, Mouza-Chandrikalapunja under Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000343/2022-2023 | 1294/TD | 13/09/2022 | 12/11/2022 | GITA ENTERPRISE | 4.85 | 3.81 | 78.39 | 100
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well I under Sapai water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001143/2022-2023 | 2124/W/MMD | 28/11/2022 | 28/03/2023 | DEBKUMAR BASU | 11.15 | 10.8 | 96.87 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional Tubewell Site (JL no. 171, Plot no. 65/215, Mouza-Chandrikalapunja) of Sapai Water Supply Scheme under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000512/2021-2022 | 1993/TD | 07/03/2022 | 28/03/2022 | PRANTIK DRILLING AGENCY | 12.08 | 8.76 | 72.52 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Rising main and other allied works for connecting Additional Tube well of Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000346/2022-2023 | 1295/TD | 13/09/2022 | 13/10/2022 | AMIT PAYRA | 4.57 | 3.48 | 76.08 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Augmentation of Sapai Water Supply Scheme by Providing Laying Distribution System and FHTC in Conati-III Block of Purba Medinipur District | Assistant Engineer | Junior Engineer | ORD/000334/2021-2022 | 1653/TD | 21/01/2022 | 21/04/2022 | ARUP KUMAR DEY | 223.76 | 205.92 | 92.03 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Supply & Delivery of CIDF Sluice Valve for laying of distribution pipe line by UPVC pipes with allied works for Augmentation of Sapai Water Supply Scheme within Contai-III Block under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000662/2021-2022 | 2224/TD | 24/03/2022 | 08/04/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.31 | 4.31 | 100 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 1866/TD | 17/02/2022 | 17/02/2022 | Resource Division | 5.42 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Repairing of 100 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir for Augmentation of Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000662/2022-2023 | 2347/TD | 10/01/2023 | 11/03/2023 | BARH CONSTRUCTION | 14.41 | 8.54 | 59.29 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Providing FHTC( Functional Household tap connection )For implementation of Har Ghar Jhal Gram / Sajal Gram under Augmentation of Sapai Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000058/2023-2024 | 133/TD | 10/04/2023 | 30/04/2023 | MRINAL KANTI PRADHAN | 10.72 | 8.12 | 75.75 | 60
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000159/2023-2024 | 1394/W/MMD | 01/06/2023 | 28/11/2023 | BHABANI PRASAD MANNA | 11.59 | 0 | 0 | 80
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Reservoir (OHR)Site, Mouza -Sapai, J.L no - 176, under Augmentation of Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. Length 76.00 mtr. | Assistant Engineer | Junior Engineer | ORD/000661/2022-2023 | 2346/TD | 10/01/2023 | 09/02/2023 | JASODA ENTERPRISE | 10.32 | 8.76 | 84.84 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Repairing Of Pump House and Boundary Wall of Pump House No-I & II under Augmentation of Sapai Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000313/2023-2024 | 486/TD | 10/05/2023 | 09/06/2023 | SADDAM DIN | 4.19 | 1.94 | 46.4 | 100
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Payment to WBSEDCL for Quotation Money of Ramchak PWSS from Sapai PWSS under Tamluk Division, PHE Dte. |  |  | BILL/00016/2023-2024 | BP-2023-24-2 | 13/04/2023 | 13/04/2023 | WBSEDCL | 0.28 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Electric Quotation bill of Sapai T/W-III ,P.O.-Bahitrakunda under Marishda CCC (Memo No. 2004155106) |  |  | BILL/00050/2022-2023 | BP-2022-23-100 | 10/01/2023 | 10/01/2023 | WBSEDCL | 0.47 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sapai | SM/09287 | Augmentation | Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method with 150 dia. uPVC Steiner of 30 m length for replacement of 1st Tube Well for Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000577/2024-2025 | 455/TD | 04/02/2025 | 16/03/2025 | PRANTIK DRILLING AGENCY | 13.3 | 0 | 0 | 0
Total | [13 empty] | 336.89 | 268.54 | 79.71