## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dhanghara Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000167/2021-2022 | 1171/TD | 01/12/2021 | 08/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 10.76 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Supply and Delivery of Different dia Sluice Valves for Dhanghara Water Supply Scheme in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000772/2022-2023 | 105 / CSD | 19/01/2023 | 03/02/2023 | BIBEKANANDA DAS | 0.95 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Supply and Delivery of Different dia Sluice Valves for Dhanghara Water Supply Scheme in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000886/2022-2023 | 439 / CSD | 20/03/2023 | 04/04/2023 | SAURAV HAZRA | 0.95 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | RESISTIVITY SURVEY AND OTHER WORKS OF DHANGHARA W/S SCHEME (TW-III), CONTAI-III BLOCK UNDER PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000398/2022-2023 | 1538/CDD | 08/12/2022 | 07/01/2023 | MENAKA ENTERPRISE | 12.67 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | CONSTRUCTION OF TUBE WELL (300MM X 200MM X DEPTH 250 MTR) FOR DHANGHARA W/S SCHEME (TW-III), CONTAI-III BLOCK WITHIN PURBA MEDINIPUR DISTRICT BY UTILISING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. |  |  | ORD/000399/2022-2023 | 413/CDD | 20/05/2022 | 19/06/2022 | KARTICK BAL | 14.67 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Supply & Delivery 80 mm dia Sluice Valve for Dhanghara W/S Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Phase-I) (Supply at Mukutshila Store) | Assistant Engineer | Junior Engineer | ORD/000359/2022-2023 | 1298/TD | 13/09/2022 | 28/09/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.9 | 0 | 0 | 100
7 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Construction of TW (300m x 200mm x 250mtr. depth) for Dhanghara WS Scheme (Rep TW-I), Contai-III Block within purba Medinipurr Dist. by utilising skilled Departmental crew and Departmental machineries of CDD, PHE Dte. |  |  | ORD/000300/2022-2023 | 412/CDD | 20/05/2022 | 19/06/2022 | KARTICK BAL | 14.67 | 0 | 0 | 100
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001466/2022-2023 | 204/W/MMD | 10/02/2023 | 09/08/2023 | M/S SREEJIT ENTERPRISE | 13.52 | 0 | 0 | 55
9 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | RESISTIVITY SURVEY AND OTHER WORKS OF Dhanghara W/S SCH (TW-I), PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000326/2022-2023 | 1537/CDD | 08/12/2022 | 07/01/2023 | MENAKA ENTERPRISE | 12.67 | 0 | 0 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 1250/TD | 13/12/2021 | 13/12/2021 | Resource Division | 10.79 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2021-2022 | 1952/TD | 04/03/2022 | 04/03/2022 | Resource Division | 18.66 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Electric Quotation for DHANGHARA Water Supply Scheme T/W-III, (Ref. ID-204049566) |  |  | BILL/01685/2023-2024 | BP-2023-24-165 | 04/08/2023 | 04/08/2023 | WBSEDCL | 1.35 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Augmentation of Dhanghara Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block Of Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000472/2021-2022 | 1947/TD | 03/03/2022 | 31/07/2022 | M/S S. S. ENTERPRISE | 547.65 | 0 | 0 | 90
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Rising main 150mm dia DI(K9) Rising main pipeline with specials and other allied works at 3rd Tube Well Site for Augmentation of Dhanghara W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000472/2023-2024 | 1498/TD | 17/07/2023 | 30/03/2025 | SUDIP MANNA | 5.27 | 0 | 0 | 100
15 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at DHANYAGARAHA Water supply scheme, contai - III block, District -Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000968/2024-2025 | 2338/W/MMD | 16/12/2024 | 14/06/2025 | P.K.ENGINEERING | 24.97 | 0 | 0 | 65
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Re-laying of Distribution pipeline, Repairing of OHR, Pump House no 1, Pump House No. 2 and Head Works Boundary Wall under JJM with allied work of Dhanghara PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000615/2024-2025 | 667/TD | 03/03/2025 | 12/04/2025 | SRIMANTA KUMAR MAITY | 23.42 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara | SM/09288 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorine Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Dhanghara Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E .Dte. Purba Medinipur (For Normal Land). | Assistant Engineer | Junior Engineer | ORD/001152/2023-2024 | 560/TD | 15/02/2024 | 12/10/2024 | GITA ENTERPRISE | 3.72 | 0 | 0 | 100
Total | [13 empty] | 720.58 | 0 | 0